## Description
The Flaw of Averages in Project Completion: Why Everything is Behind Schedule
Experiment with the Release Target
on the Model Sheet
Copyright © 2013 ProbabilityManagement.org, all rights reserved.
www.probabilitymanagement.org
Release Date given the Average Task Durations is 6 weeks
Actual Average Release Date is 7.8 weeks
Scroll through duration scenarios here
The Release Date formula (D19) drives the Data Table on the PMTable sheet while running duration scenarios through cells D8 through D17.
Adjust Release Target and see your chances of meeting it
Distribution of Actual Time to Release
Uncertain Durations
Uncertain Durations
Uncertain Durations
The Average Project Completion Time is greater than that predicted by the Average Durations of the underlying tasks, because the project is not done until the last task is done

## Model
[11 empty] | 20 | 20
Schedule
| Scenario 20 | Completing a Software Project
|  | weeks to release |  |  |  | 7.66
Task | Time to Complete | [6 empty] | Average | Target | Chance
Description | in weeks | [5 empty] | Released | 7.8405 | 8 | 57.7%
Subroutine 1 | 5.45 |  | 0 | 7.66 | 0
Subroutine 2 | 6.01 |  | 0 | 0
Subroutine 3 | 4.65 |  | 4.38 | 0 | 0
Subroutine 4 | 4.08 |  | 3.37 | 0 | 0
Subroutine 5 | 5.54 |  | 6.67 | 0 | 0
Subroutine 6 | 5.18 |  | 7.66 | 0 | 0
Subroutine 7 | 7.66 |  | 5.18 | 0 | 0
Subroutine 8 | 6.67 |  | 5.54 | 0 | 0
Subroutine 9 | 3.37 |  | 4.08 | 0 | 0
Subroutine 10 | 4.38 |  | 4.65 | 0 | 0
|  |  | 6.01 | 0 | 0
Released | 7.66 |  | 5.45 | 0 | 0
Copyright © 2013 ProbabilityManagement.org, all rights reserved.
www.probabilitymanagement.org
Note on Q7: Chance of finishng in targeted number of weeks or less
Note on Q26: Chance of penalty of targeted amount or less

## Library
Subroutines - Duration in Weeks
Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | Sub 8 | Sub 9 | Sub 10
7.56 | 5 | 5.11 | 7.38 | 7.26 | 3.76 | 6.41 | 4.4 | 5.19 | 7.68 | 1000 | Number of trials
4.95 | 5.81 | 5.94 | 7.82 | 5.06 | 4.62 | 5.43 | 6.07 | 4.62 | 6.45
6.12 | 4.04 | 7.05 | 5.63 | 5.23 | 5.4 | 4.39 | 5.89 | 6.24 | 5.98 | Table position of Average
7.03 | 7.61 | 5.55 | 7.13 | 5.17 | 4.26 | 7.77 | 4.36 | 6.61 | 6.5 | 1001
7.53 | 5.75 | 3.8 | 6.01 | 6.86 | 6.98 | 6.36 | 4.39 | 7.49 | 6.36
6.64 | 7.96 | 6.08 | 4.83 | 7.45 | 5.66 | 4.77 | 7.84 | 5.28 | 5.52
4.28 | 4.83 | 5.45 | 5.68 | 3.72 | 6.23 | 3.61 | 7.26 | 4.5 | 6.48
3.97 | 4.17 | 7.83 | 6.42 | 4.99 | 6.88 | 6.8 | 7.6 | 3.84 | 6.09
6.36 | 6.54 | 5.13 | 5.33 | 4.81 | 5.62 | 3.09 | 7.2 | 5.47 | 4.74
6.7 | 3.37 | 6.51 | 5 | 4.32 | 4.86 | 6.03 | 6.41 | 6.15 | 4.15
7.79 | 7.7 | 5.81 | 5.6 | 4.74 | 4.81 | 6.34 | 5.68 | 6.51 | 4.44
7.22 | 5.28 | 6.23 | 7.57 | 5.65 | 6.77 | 6.98 | 4.76 | 6.27 | 7.47
6.27 | 4.26 | 4.82 | 6.1 | 5.19 | 8.01 | 6.9 | 5.41 | 7.13 | 8.22
5 | 5.01 | 5.54 | 5.43 | 3.47 | 6.71 | 6.38 | 6.42 | 5.61 | 5.87
5.87 | 6.04 | 6.44 | 7.4 | 5.94 | 5.81 | 4.89 | 8.79 | 7.56 | 5.17
6.08 | 7.3 | 7.36 | 4.98 | 7.63 | 5.19 | 5.45 | 6.71 | 6.77 | 4.34
6.35 | 5.25 | 7.84 | 6.94 | 5.27 | 5.95 | 6.22 | 4.46 | 6.42 | 6.39
5.77 | 6.18 | 6.12 | 5.74 | 6.65 | 6.58 | 8.2 | 5.8 | 4.77 | 5.6
6.49 | 8.28 | 5.84 | 4.5 | 3.34 | 3.89 | 4.97 | 8.31 | 5.05 | 7.87
5.45 | 6.01 | 4.65 | 4.08 | 5.54 | 5.18 | 7.66 | 6.67 | 3.37 | 4.38
7.39 | 8.24 | 5.71 | 6.71 | 5.81 | 5.92 | 8.36 | 5.75 | 5.38 | 8.14
5.32 | 6.59 | 7.09 | 4.6 | 6.56 | 5.83 | 7.6 | 5.76 | 4.48 | 4.58
3.21 | 5.97 | 6.27 | 6.92 | 5.76 | 5.83 | 8 | 7.48 | 4.93 | 5.46
5.61 | 5.64 | 4.89 | 5.9 | 4.84 | 7.23 | 4.96 | 7.17 | 6.75 | 7.95
6.01 | 5.58 | 5.7 | 7.59 | 4.67 | 5.46 | 6.89 | 3.83 | 4.15 | 6.51
7.57 | 7.1 | 4.99 | 4.03 | 4.85 | 5.85 | 5.66 | 7.34 | 6.15 | 7.35
3.89 | 6.67 | 4.6 | 6.55 | 6.67 | 5.39 | 4.69 | 8.08 | 6.63 | 6.14
4.98 | 5.88 | 6.56 | 5.86 | 4.25 | 5.43 | 5.64 | 6.16 | 5.44 | 6.77
4.63 | 5.44 | 4.67 | 5.22 | 3.39 | 6.09 | 5.97 | 6.01 | 5.01 | 5.98
6.18 | 7.77 | 8.22 | 5.79 | 5.27 | 4.91 | 7.04 | 3.81 | 6.73 | 5.5
6.71 | 5.05 | 5.59 | 6.16 | 7.43 | 5.17 | 5.31 | 6.57 | 7.99 | 5.32
6.77 | 5.85 | 7.74 | 5.23 | 3.89 | 4.98 | 6.59 | 7.24 | 3.41 | 7.39
7.58 | 5.47 | 5.76 | 8.09 | 6.75 | 7.7 | 6.4 | 6.77 | 8.55 | 6.27
7.5 | 5.4 | 4.42 | 7.75 | 5.93 | 6.2 | 5.87 | 5.93 | 6.08 | 5.82
4.62 | 8.1 | 6.26 | 4.22 | 3.51 | 5.08 | 6.25 | 7.54 | 4.89 | 6.86
5.84 | 6.61 | 6.79 | 7.02 | 5.73 | 5.45 | 6.08 | 5.53 | 6.28 | 5.24
5.34 | 7.14 | 4.44 | 5.75 | 5.68 | 6.8 | 6.17 | 6.12 | 3.96 | 3.91
4.96 | 6.81 | 6.15 | 4.13 | 6.33 | 5.26 | 5.21 | 3.54 | 8.08 | 6.46
5.42 | 6.44 | 5.83 | 8.61 | 6.22 | 7.06 | 6.81 | 4.95 | 4.6 | 6.71
4.22 | 4.62 | 5.99 | 6.1 | 7.22 | 6.92 | 7.04 | 4.84 | 6.87 | 7.43
6.62 | 4.01 | 5.66 | 5.99 | 8.2 | 6.95 | 8.14 | 4.14 | 5.31 | 4.52
5.69 | 4.99 | 6.22 | 7.34 | 6.98 | 6.54 | 4.37 | 6.48 | 6.28 | 7.28
6.42 | 8.17 | 4.06 | 7.46 | 4.66 | 4.84 | 5.62 | 7.05 | 7.32 | 7.97
6.02 | 3.82 | 4.83 | 5.57 | 5.96 | 5.15 | 7.13 | 5.21 | 7.88 | 4.83
8.17 | 5.94 | 7.16 | 6.57 | 5.71 | 5.48 | 6.33 | 5.12 | 5.66 | 5.42
7.99 | 7.27 | 8.59 | 6.24 | 7.23 | 6.26 | 7.56 | 7.24 | 7.41 | 5.47
4.89 | 5.15 | 4.03 | 4.81 | 7 | 5.49 | 5.17 | 5.6 | 4.45 | 4.29
6.35 | 6.33 | 8.01 | 6.52 | 4.63 | 6.81 | 5.08 | 4.34 | 6.51 | 5.25
3.72 | 4.1 | 4.13 | 7.52 | 4.92 | 6.5 | 4.57 | 6.74 | 4.59 | 6.54
4.55 | 5.67 | 6.56 | 5.97 | 6.55 | 6.67 | 6.54 | 5.47 | 5.95 | 3.61
7.65 | 4.7 | 6.73 | 4.88 | 8.21 | 6.43 | 3.96 | 4.92 | 5.21 | 6.26
5.31 | 4.3 | 5.71 | 4.59 | 7.73 | 5.42 | 5 | 5.52 | 5.68 | 7.67
7.58 | 6.92 | 6.36 | 6.41 | 5.37 | 6.19 | 7.17 | 4.45 | 6.22 | 4.32
6.33 | 3.54 | 5.69 | 6.03 | 5.98 | 7.16 | 6.58 | 8.16 | 4.91 | 6.81
5.96 | 4.21 | 8.13 | 6.67 | 6.41 | 7.78 | 7.95 | 8.01 | 6.56 | 5.34
5.72 | 5.23 | 6.64 | 7.72 | 3.96 | 7.27 | 7.94 | 7.02 | 7.53 | 6.53
6.93 | 6.73 | 6 | 4.12 | 7.84 | 4.32 | 4.53 | 6.87 | 5.14 | 5.28
5.25 | 6.52 | 7.01 | 5.59 | 4.86 | 6.34 | 7.08 | 5.51 | 7.04 | 4.47
5.31 | 5.78 | 8.15 | 7.04 | 3.79 | 7.16 | 6.86 | 8.27 | 4.86 | 5.7
6.54 | 5.94 | 7.26 | 5.56 | 5.58 | 3.91 | 3.25 | 8.17 | 5.02 | 4.95
4.37 | 4.44 | 5.63 | 4.37 | 5 | 6.75 | 7.21 | 6.35 | 3.16 | 5.19
6.66 | 6.12 | 6.27 | 6.36 | 5.5 | 5.98 | 5.56 | 7.87 | 5.15 | 6.86
6.45 | 8.09 | 7.82 | 5.28 | 7.62 | 6.94 | 6.8 | 3.58 | 7.3 | 5.1
6.14 | 7.53 | 6.36 | 6.52 | 5.46 | 5.14 | 5.41 | 4.7 | 6.78 | 6.91
6.1 | 5.18 | 5.45 | 6.67 | 4.01 | 7 | 6.26 | 4.77 | 5.09 | 7.31
5.34 | 6.41 | 8.75 | 6.79 | 4.96 | 6.15 | 7.51 | 6.84 | 4.54 | 8.06
4.33 | 6.36 | 6.27 | 6.54 | 7.52 | 5.93 | 5.39 | 6.77 | 6.7 | 5.99
5.42 | 6.52 | 5.81 | 7.62 | 7.72 | 4.59 | 5.28 | 4.48 | 6.45 | 5.92
6.03 | 8.63 | 4.24 | 5.73 | 6.14 | 7.26 | 4.1 | 4.47 | 5.23 | 7.06
4.28 | 6.07 | 6.4 | 5.53 | 7.35 | 6.22 | 4.88 | 6.36 | 6.2 | 7.37
3.98 | 4.89 | 5.68 | 6.83 | 7.56 | 6.99 | 5.14 | 6.2 | 7.75 | 5.39
3.87 | 4.72 | 5.53 | 3.97 | 6.21 | 5.25 | 6.13 | 5.17 | 5.1 | 5.84
6.19 | 6.61 | 5.14 | 6.48 | 5.89 | 6.07 | 5.25 | 6.5 | 6.08 | 5.94
8.61 | 4.84 | 4.68 | 8.15 | 6.42 | 3.81 | 6.59 | 5.05 | 6.02 | 7.13
6.55 | 7.25 | 5.36 | 4.1 | 7.37 | 5.49 | 7.93 | 4.99 | 6.58 | 8.02
8.32 | 4.8 | 7.28 | 4.53 | 8 | 5.85 | 6.01 | 6.02 | 6.01 | 4.54
5.23 | 5.52 | 5.01 | 4.65 | 7.32 | 7.56 | 8.84 | 6.95 | 5.6 | 4.5
8.22 | 4.92 | 6.1 | 5.88 | 5.29 | 5.56 | 6.04 | 6.22 | 5.71 | 7.66
5.55 | 4.96 | 7.51 | 5.91 | 6.05 | 5.01 | 4.14 | 3.72 | 6.77 | 4.18
7.4 | 6.46 | 5.87 | 6.18 | 8.03 | 4.17 | 5.98 | 7.55 | 6.73 | 7.2
6.21 | 8.84 | 4.02 | 6.15 | 6.98 | 4.15 | 8.49 | 7.12 | 5.32 | 8.39
5.88 | 6.66 | 5.18 | 6.33 | 5.13 | 7.36 | 6.75 | 6.47 | 8.03 | 7.02
6.36 | 5.91 | 5.02 | 5.01 | 4.93 | 4.73 | 3.49 | 5.19 | 5.82 | 5.72
6.08 | 4.42 | 7.1 | 7.76 | 7.36 | 5.51 | 5.3 | 6.26 | 8.27 | 5.03
3.75 | 4.13 | 3.79 | 5.81 | 5.8 | 6.68 | 4.85 | 6.75 | 4.79 | 6.88
6.2 | 4.98 | 6.63 | 7.07 | 6.36 | 6.63 | 4.58 | 8 | 7.25 | 4.03
7.47 | 6.54 | 5.25 | 5.77 | 6.36 | 6.14 | 7.58 | 6.34 | 7.89 | 6.4
7.25 | 6.55 | 5.85 | 7.42 | 4.57 | 5.74 | 6.27 | 4.86 | 7.26 | 4.08
7.13 | 5.53 | 5.31 | 6.22 | 4.73 | 5.12 | 5.74 | 3.76 | 4.96 | 7.6
6.9 | 5.74 | 5.04 | 6.82 | 4.78 | 3.58 | 4.56 | 7.39 | 7.11 | 7.52
6.72 | 3.59 | 5.09 | 3.93 | 7.4 | 6.11 | 4.03 | 4.57 | 5.77 | 6.56
7.8 | 5.89 | 3.82 | 5.03 | 4.17 | 7.38 | 6.22 | 5.73 | 5.52 | 4.26
6.8 | 4.49 | 6.99 | 5.14 | 7.1 | 6.94 | 4.96 | 4.9 | 5.01 | 8.2
6.58 | 6.51 | 5.79 | 6.4 | 5.79 | 8.38 | 5.45 | 5.1 | 8.13 | 5.29
4.47 | 4.75 | 5.8 | 4.29 | 4.72 | 6.89 | 5.92 | 5.32 | 8.21 | 7.49
5.75 | 5.49 | 7.64 | 5.92 | 5.16 | 6.54 | 6.27 | 4.62 | 4.78 | 8.61
6.4 | 8.13 | 6.45 | 6.28 | 5.17 | 5 | 5.69 | 5.24 | 7.43 | 6.46
7.17 | 3.68 | 3.59 | 4.09 | 6.14 | 5.3 | 6.26 | 8.34 | 4.86 | 7.56
5.01 | 5.05 | 4.93 | 6.12 | 6.33 | 4.68 | 4.47 | 5.22 | 4.95 | 6.51
4.14 | 6.64 | 4.9 | 6.94 | 4.87 | 7.99 | 7.9 | 7 | 7.66 | 6.6
6.95 | 7.52 | 6.93 | 5.08 | 8.13 | 5.25 | 4.21 | 6.1 | 6.16 | 4.44
7.82 | 5.68 | 6.67 | 4.2 | 7.17 | 5.59 | 6.07 | 6.28 | 7.28 | 5.17
5.56 | 3.84 | 5.92 | 6.03 | 5.88 | 5.99 | 6.11 | 6.39 | 6.16 | 6.82
7 | 7.35 | 6.26 | 4.62 | 7.17 | 3.37 | 6.82 | 6.45 | 5.78 | 6.23
6.75 | 5.21 | 6.08 | 4.55 | 3.28 | 6.97 | 8.28 | 7.76 | 5.33 | 4.33
6.28 | 6.95 | 5.19 | 4.47 | 6.02 | 6.79 | 4.86 | 5.17 | 6.67 | 6.89
4.56 | 6.08 | 4.81 | 5.17 | 6.37 | 5.37 | 8.42 | 6.44 | 4.77 | 5.07
5.85 | 6.4 | 6.16 | 3.53 | 4.47 | 7.02 | 7.81 | 7.53 | 7.48 | 4.74
4.86 | 4.95 | 4.53 | 6.39 | 6.41 | 7.35 | 6.25 | 4.19 | 3.9 | 6.25
5.57 | 6.07 | 7.77 | 4.87 | 5.52 | 4.99 | 6.44 | 6.96 | 6.14 | 5.62
5.91 | 5.78 | 5.2 | 8.3 | 7.11 | 4.94 | 5.13 | 5.98 | 6.09 | 5.8
4.48 | 4.81 | 5.21 | 6.33 | 5.38 | 6.66 | 6.7 | 7.01 | 8.26 | 5.59
5.94 | 5.89 | 5.6 | 5.52 | 7.31 | 6.11 | 6.69 | 8.02 | 7.06 | 5.71
5.41 | 5.63 | 8.05 | 5.99 | 6.18 | 5.96 | 5.48 | 4.5 | 7.18 | 4.86
3.78 | 5.99 | 3.98 | 5.55 | 6.73 | 6.53 | 5.18 | 4.04 | 5.9 | 3.65
7.72 | 7.65 | 5.72 | 6.87 | 5.11 | 6.22 | 6.71 | 5.39 | 5.19 | 5.43
6.94 | 3.41 | 3.87 | 6.77 | 4.42 | 5.19 | 7.65 | 5.45 | 6.89 | 5.41
3.41 | 7.21 | 7.04 | 7.89 | 7.82 | 4 | 6.67 | 7.07 | 5.07 | 7.1
6.64 | 6.09 | 6.1 | 6.91 | 4.48 | 8.55 | 5.82 | 6.64 | 7.24 | 6
4.58 | 6.05 | 4.34 | 5.41 | 7.95 | 5.64 | 6.95 | 6.14 | 5.84 | 7.53
6.17 | 8.27 | 8.35 | 7.43 | 7.61 | 5.33 | 6.24 | 6.03 | 5.88 | 3.47
5.14 | 5.31 | 4.22 | 6.38 | 3.62 | 5.14 | 5.34 | 4.21 | 6.33 | 6.25
8.27 | 7.43 | 5.29 | 4.47 | 6.96 | 5.15 | 4.26 | 7.2 | 5.48 | 4.32
5.93 | 5.41 | 6.82 | 4.18 | 7.19 | 4.42 | 8.03 | 5.25 | 4.5 | 6.95
4.91 | 6.56 | 5.53 | 5.52 | 6.7 | 7.14 | 4.13 | 5.71 | 4.92 | 6.48
8.39 | 7.94 | 5.03 | 6.16 | 5.69 | 7.62 | 5.72 | 5.7 | 7.54 | 6.01
5.73 | 4.99 | 6.86 | 5.21 | 4.39 | 5.05 | 3.79 | 7.18 | 8.63 | 5.65
7.14 | 7.21 | 7.58 | 7.96 | 8.91 | 8.14 | 5.59 | 6.65 | 6.22 | 4.65
3.62 | 4.94 | 3.31 | 3.92 | 7.39 | 4.83 | 6.47 | 5.32 | 4.22 | 6.9
8.26 | 6.27 | 5.58 | 8.35 | 5.77 | 5.35 | 5.16 | 4.88 | 7.77 | 6.11
3.8 | 7.87 | 5.8 | 6.9 | 5.43 | 5.17 | 6.81 | 6.19 | 5.91 | 3.53
5.12 | 5.17 | 6.07 | 6.89 | 6.27 | 7.32 | 4.04 | 6.12 | 7.16 | 6.66
6.21 | 6.07 | 6.52 | 6.21 | 6.54 | 5.43 | 8.46 | 5.01 | 5.71 | 7.72
5.6 | 6.02 | 6.04 | 5.21 | 7.54 | 6.66 | 5.83 | 7.72 | 5.25 | 6.81
5.61 | 7.82 | 7.52 | 4.61 | 5.42 | 6.99 | 7.27 | 4.68 | 7.17 | 7.46
6.96 | 7.15 | 5.29 | 6.34 | 6.86 | 5.72 | 6.95 | 7.68 | 5.56 | 4.09
3.91 | 6.82 | 6.25 | 4.54 | 7.52 | 4.14 | 5.36 | 6.14 | 3.47 | 6.95
5.2 | 5.68 | 5 | 6.33 | 4.3 | 7.06 | 6.25 | 5.82 | 5.14 | 4.94
6.24 | 4.79 | 5.57 | 6.45 | 6.9 | 4.86 | 7.12 | 3.34 | 6.47 | 5.64
5.34 | 5.73 | 5.76 | 7.87 | 7.01 | 6.58 | 4.47 | 6.1 | 6.5 | 5.54
6.53 | 5.67 | 5.96 | 5.61 | 5.91 | 3.92 | 5.43 | 5.96 | 5.31 | 6.65
3.54 | 6.5 | 4.04 | 6.35 | 7.04 | 7.07 | 4.48 | 4.17 | 6.02 | 5.79
6.76 | 5.82 | 6.79 | 5.08 | 5.25 | 5.57 | 5.16 | 6.61 | 5.66 | 6.58
8.16 | 5.27 | 7.69 | 6 | 6.53 | 6.06 | 5.85 | 5.77 | 5.59 | 8.04
5.8 | 6.78 | 5.91 | 5.8 | 6.23 | 6.2 | 4.01 | 7.34 | 6.12 | 6.77
7.11 | 5.79 | 7.45 | 5.19 | 6.72 | 4.65 | 4.94 | 6.51 | 5.94 | 4.04
6 | 5.74 | 4.87 | 7.5 | 6.78 | 6.7 | 6 | 6.59 | 4.85 | 6.84
6.22 | 6.8 | 6.35 | 6.25 | 7.08 | 4.94 | 7.34 | 4.85 | 7.82 | 5.26
6.4 | 8.3 | 3.94 | 4.97 | 4.37 | 5.35 | 4.6 | 4.13 | 6.81 | 7.7
3.99 | 4.75 | 8.46 | 6.66 | 5.05 | 7.65 | 3.64 | 7.3 | 4.7 | 5.69
7.07 | 6.24 | 5.5 | 4.99 | 3.81 | 8.18 | 6.62 | 6.45 | 4.39 | 6.62
4.95 | 8.26 | 5.26 | 7.86 | 4.28 | 7 | 4 | 7.43 | 7.7 | 8.25
6.52 | 6.77 | 8.06 | 5.2 | 4.89 | 8.2 | 6.34 | 6.37 | 6.34 | 5.58
5.02 | 6.75 | 3.88 | 4.8 | 4.89 | 7.97 | 7.61 | 7.66 | 5.93 | 4.96
8.05 | 8.42 | 7.9 | 6.86 | 7.99 | 4.32 | 8.27 | 6.36 | 5.39 | 7.51
6.43 | 5.01 | 6.1 | 5.71 | 5.74 | 5.41 | 5.01 | 5 | 6.27 | 5.04
5.69 | 4.54 | 4.17 | 6.69 | 7.66 | 7.17 | 7.08 | 7.59 | 8.35 | 4.51
5.81 | 6.34 | 4.92 | 6.58 | 5.34 | 6.21 | 6.01 | 6.05 | 6.46 | 5.89
6.44 | 6.27 | 6.38 | 6.22 | 5.22 | 7.57 | 6.12 | 6.09 | 4.03 | 4.11
4.85 | 5.62 | 4.85 | 5.67 | 5.41 | 4.1 | 7.01 | 3.93 | 4.65 | 7.97
5.3 | 7.89 | 8.63 | 7.94 | 7.65 | 7.53 | 5.67 | 6 | 4.51 | 3.99
6.07 | 4.89 | 4.78 | 6.64 | 8.12 | 3.8 | 7.19 | 7.04 | 8.34 | 6.57
8.42 | 5.12 | 5.54 | 6.71 | 6.34 | 6.73 | 6.94 | 5.98 | 4.01 | 7.4
7.12 | 7.08 | 4.32 | 4.05 | 8.75 | 5.78 | 8.44 | 5.85 | 7.34 | 6.4
5.36 | 6.98 | 7.59 | 4.69 | 5.79 | 4.29 | 8.57 | 6.04 | 7.55 | 7.49
5.97 | 8.47 | 5.95 | 4.92 | 7.44 | 4.11 | 5.38 | 6.93 | 8.19 | 6.2
7.22 | 4.13 | 5.81 | 6.76 | 5.35 | 3.64 | 6.68 | 8.24 | 7.37 | 6.21
7.88 | 7.42 | 6.01 | 7.85 | 6.09 | 5.11 | 3.74 | 5.93 | 5.17 | 6.68
8.72 | 7.01 | 4.81 | 8.42 | 5.75 | 6.2 | 7.16 | 6.8 | 6.33 | 4.4
5.79 | 5.21 | 7.7 | 7.52 | 6.24 | 5.62 | 5.6 | 6.97 | 8.1 | 7.62
6.97 | 5.11 | 6.38 | 5.05 | 4.76 | 7.37 | 6.51 | 5.16 | 4.36 | 5.1
6.74 | 7.64 | 6.72 | 3.39 | 7.44 | 5.63 | 5.12 | 4.74 | 3.82 | 7.3
8.03 | 5.92 | 3.9 | 4.58 | 5.16 | 4.45 | 5.95 | 5.94 | 5.58 | 5.63
7.26 | 4.92 | 7.72 | 5.89 | 6.5 | 6.52 | 4.86 | 6.53 | 7.62 | 6.49
6.14 | 3.21 | 5.26 | 3.99 | 7.69 | 6.07 | 7.22 | 5.71 | 5.42 | 8.15
6.27 | 5.51 | 6.04 | 4.66 | 4.56 | 7.33 | 7.53 | 7.72 | 7.83 | 5.73
5.01 | 6.67 | 5.52 | 6.88 | 7.28 | 7.46 | 4.32 | 5.49 | 3.78 | 6.17
5.03 | 5.63 | 4.74 | 8.49 | 5.39 | 6.78 | 6.28 | 5.09 | 8.09 | 4.57
4.2 | 4.64 | 6.68 | 7.55 | 7.14 | 6.48 | 6.7 | 6.05 | 6.97 | 5.33
4.74 | 6.61 | 5.16 | 6.13 | 7.58 | 4.87 | 4.28 | 3.31 | 5.97 | 7.92
7.24 | 6.2 | 4.33 | 5.68 | 5.4 | 4.49 | 6.38 | 7.33 | 7.57 | 5.83
5.05 | 6.49 | 5.99 | 7.45 | 7.06 | 6.45 | 6.1 | 8.91 | 5.05 | 6.65
5.14 | 4.25 | 4.2 | 4.73 | 5.97 | 4.4 | 4.15 | 5.48 | 4.74 | 3.86
5.01 | 3.76 | 4.91 | 3.64 | 7.71 | 8.36 | 5.98 | 5.54 | 5.46 | 8.08
3.61 | 5.59 | 6.66 | 7.04 | 5.03 | 7.56 | 6.21 | 6.82 | 4.53 | 5.39
5.48 | 6.47 | 7.11 | 7.28 | 4.48 | 6.92 | 6.12 | 5.49 | 5.54 | 7.04
6.47 | 5.24 | 6 | 6.37 | 5.5 | 5.74 | 3.37 | 5.25 | 5.82 | 6.02
5.66 | 5.59 | 5.75 | 4.78 | 8.31 | 5.67 | 5.12 | 5.35 | 4.75 | 5.76
4.77 | 8.25 | 5.39 | 8.13 | 7.75 | 6.72 | 6.66 | 4.7 | 6.4 | 6.16
4.03 | 7.64 | 5.32 | 6.08 | 4.98 | 6.2 | 5.63 | 6.81 | 8.69 | 6.71
4.4 | 4.95 | 5.32 | 5.34 | 6.08 | 5.68 | 6.83 | 7.36 | 6.64 | 4.92
6.98 | 4.43 | 5.67 | 7.81 | 5.48 | 6.16 | 4.09 | 3.9 | 6.69 | 6.1
7.21 | 6.82 | 5.3 | 6.88 | 8.26 | 6.45 | 5.23 | 5.68 | 6.54 | 7.5
7.42 | 5.17 | 4.21 | 5.39 | 7.07 | 6.15 | 4.9 | 6.55 | 5.37 | 6.25
5.59 | 6.93 | 4.69 | 7.5 | 4.51 | 5.13 | 7.46 | 4.93 | 8.79 | 6.83
5.94 | 5.93 | 5.98 | 4.41 | 5.56 | 5.86 | 4.44 | 5.86 | 5.8 | 6.85
7.86 | 8.61 | 3.51 | 6.41 | 8.49 | 6.81 | 4.38 | 4.61 | 6.37 | 5.66
6.59 | 6.33 | 4.17 | 6.83 | 5.73 | 6.35 | 7.24 | 7.41 | 7.52 | 5.95
5.49 | 6.43 | 6.37 | 7.35 | 7.75 | 4.6 | 5.77 | 6.03 | 6.69 | 7.71
5.71 | 5.52 | 4.93 | 4.2 | 5.21 | 7.17 | 7.62 | 4.67 | 8.53 | 6.45
6.08 | 4.03 | 6.44 | 6.17 | 6.09 | 8.19 | 6.83 | 4.45 | 6.1 | 7.09
3.82 | 5.84 | 8.3 | 8.21 | 6.19 | 7.5 | 7.69 | 5.19 | 6.48 | 6.05
7.74 | 7.53 | 7.68 | 6.56 | 5.19 | 4.97 | 5.05 | 4.88 | 3.85 | 3.69
8.09 | 7.09 | 4.51 | 5.55 | 7.91 | 4.25 | 5.86 | 4.2 | 5.03 | 4.17
7.93 | 8.39 | 5.56 | 6.79 | 6.48 | 5.53 | 5.71 | 5.08 | 7.45 | 5.59
6.71 | 5.98 | 5.43 | 5.72 | 7.46 | 6.18 | 8.26 | 3.43 | 5.94 | 7.57
3.94 | 5.19 | 4.37 | 5.24 | 6.01 | 7.51 | 5.05 | 4.91 | 6.07 | 7.25
7.38 | 7.34 | 6.81 | 7.31 | 7.08 | 6.69 | 5.78 | 4.94 | 7.31 | 4.21
5.51 | 6.87 | 5.13 | 6.92 | 5.59 | 7.41 | 8.01 | 6.65 | 5.81 | 7.31
5.42 | 5.5 | 4.77 | 7.03 | 7.19 | 6.33 | 5.52 | 5.95 | 5.86 | 3.31
5.49 | 5.65 | 6.53 | 8.72 | 3.16 | 5.85 | 5.2 | 6.9 | 4.45 | 5.86
4.45 | 4.87 | 5.15 | 5.26 | 5.72 | 5.41 | 8.69 | 6 | 6.96 | 4.79
8.13 | 5.5 | 6.86 | 5.42 | 6.04 | 6.57 | 7.58 | 6.08 | 4.98 | 6.74
5.11 | 6.25 | 5.55 | 5.85 | 5.61 | 7.63 | 3.39 | 4.65 | 7.27 | 5.63
6.09 | 3.53 | 7.34 | 6.7 | 5.01 | 5.47 | 4.59 | 7.33 | 6.12 | 5.27
8.35 | 3.61 | 5 | 7.33 | 6.62 | 5.63 | 5.08 | 6.14 | 6.8 | 4.23
6.33 | 5.02 | 4.2 | 7.41 | 6.59 | 4.9 | 7.88 | 5.44 | 3.8 | 6.68
6 | 6.06 | 7.62 | 6.69 | 5.02 | 5.98 | 7.49 | 7.11 | 3.65 | 6.8
3.7 | 6.95 | 5.53 | 5.01 | 3.37 | 7.28 | 5.81 | 5.26 | 7.22 | 6.66
7.16 | 4.36 | 7.28 | 7.64 | 7.15 | 4.18 | 3.97 | 5.88 | 6.28 | 5.85
5.78 | 4.91 | 5.19 | 5.63 | 5.78 | 6.16 | 3.83 | 6.58 | 7.34 | 4.28
4.93 | 5.35 | 4.7 | 6.05 | 5.32 | 7.05 | 5.56 | 3.89 | 3.09 | 5.14
7.46 | 4.77 | 5.75 | 8.06 | 8.39 | 5.02 | 6.58 | 5.22 | 5.7 | 6.2
6.18 | 5.29 | 6.05 | 5.24 | 6.81 | 5.81 | 6.19 | 4.5 | 6.47 | 4.62
5.66 | 5.14 | 6.03 | 5.56 | 4.09 | 7.77 | 6.48 | 4.68 | 5.88 | 6.47
5.59 | 6.01 | 7.37 | 3.37 | 5.34 | 4.56 | 7.02 | 6.32 | 5.16 | 6.08
6.1 | 5.07 | 6.85 | 7.74 | 4.58 | 4.82 | 6.16 | 6.2 | 4.74 | 3.97
6.74 | 8.41 | 5.12 | 6.8 | 4.23 | 5 | 5.5 | 6.54 | 5.29 | 6.89
6.1 | 6.6 | 6.08 | 3.69 | 6.17 | 7.53 | 5.99 | 6.49 | 6.39 | 4.48
7.14 | 5.88 | 6.97 | 3.62 | 7.21 | 7.34 | 6.79 | 6.48 | 4.02 | 4.83
3.09 | 5.83 | 4.53 | 7.06 | 6.11 | 8.79 | 6.27 | 4 | 6.14 | 6.38
6.05 | 4.83 | 5.48 | 6.2 | 4 | 7.87 | 4.33 | 6.5 | 7.28 | 8.05
6.73 | 4.73 | 5.41 | 3.09 | 6.18 | 6.68 | 5.67 | 6.63 | 6.81 | 6.24
8.47 | 5.85 | 6.91 | 4.42 | 6.63 | 4.84 | 5.44 | 7.03 | 6.17 | 6.61
7.91 | 6.45 | 6.51 | 3.65 | 5.93 | 6.03 | 6.18 | 6.55 | 4.54 | 6.16
5.58 | 4.16 | 5.21 | 4.13 | 7.83 | 4.33 | 7.59 | 7.01 | 4.47 | 7.69
5.53 | 7.04 | 4.36 | 6.14 | 7.16 | 5.9 | 5.31 | 4.47 | 7.93 | 8.1
7.01 | 5.33 | 4.01 | 5.31 | 4.41 | 8.09 | 7.34 | 6.41 | 6.44 | 6.9
6.23 | 4.72 | 3.93 | 6.59 | 6.87 | 5.75 | 5.55 | 6.53 | 3.76 | 3.95
5.63 | 3.78 | 3.78 | 4.25 | 8.1 | 5.6 | 8.24 | 7.19 | 4.52 | 5.97
5.8 | 6.28 | 5.85 | 6.77 | 7.18 | 8.51 | 5.66 | 5.67 | 6.77 | 4.38
5.39 | 7.14 | 6.76 | 5.18 | 6.6 | 6.37 | 8.17 | 7.15 | 5.08 | 8.91
7.3 | 5.13 | 7.88 | 5.67 | 4.95 | 5.7 | 4.74 | 6.08 | 5.29 | 4.73
5.25 | 7.3 | 6.32 | 5.48 | 6 | 7.02 | 7.07 | 6.85 | 4.62 | 6.12
4 | 5.73 | 6.69 | 6.43 | 4.4 | 7.62 | 6.25 | 6.4 | 5.8 | 6.39
4.57 | 5.34 | 5.41 | 6.17 | 6.67 | 4.53 | 6.6 | 8.38 | 4.89 | 7.19
6.61 | 6.1 | 6.19 | 5.47 | 6.92 | 8.21 | 7.09 | 3.56 | 7.56 | 5.52
4.25 | 7.83 | 5.85 | 6.35 | 7.5 | 6.71 | 5.36 | 7.46 | 4.29 | 7.77
5.28 | 7.54 | 4.72 | 7.66 | 5.6 | 7.27 | 5.88 | 6.92 | 7.12 | 6.99
6.42 | 8.01 | 4.99 | 6.85 | 6.68 | 5.44 | 4.64 | 5.79 | 6.36 | 4.25
6.46 | 6.39 | 3.45 | 5.05 | 8.59 | 4.38 | 7.98 | 6.38 | 4.09 | 6.05
7.35 | 6.03 | 6.25 | 6.2 | 5.45 | 4.28 | 7.73 | 5.31 | 6.37 | 6.56
5.28 | 7 | 5.94 | 6.25 | 5.55 | 4.79 | 7.39 | 5.83 | 4.76 | 5.78
7.09 | 7.72 | 7.01 | 6.99 | 5.23 | 6.64 | 6.63 | 5.05 | 6.83 | 6.55
6.87 | 6.53 | 5.31 | 3.95 | 5.91 | 6.36 | 3.58 | 7.55 | 7.26 | 7
8.46 | 4.65 | 6.07 | 3.83 | 4.96 | 6.76 | 5.9 | 5.8 | 8.24 | 5.82
7.92 | 6.11 | 5.96 | 4.88 | 5.37 | 5.65 | 4.38 | 8.47 | 6.67 | 5.9
6.08 | 6.12 | 6.09 | 4.62 | 7.18 | 5.7 | 6.92 | 7.42 | 4.66 | 4.96
3.88 | 6.25 | 4.62 | 5.78 | 5.07 | 6.19 | 8.47 | 5.65 | 7.53 | 7.35
7.75 | 6.48 | 3.34 | 5.79 | 5.61 | 6.03 | 4.03 | 4.77 | 3.58 | 5.5
7.66 | 6.65 | 5.1 | 5.66 | 8.17 | 4.97 | 6.36 | 5.5 | 5.27 | 5.48
6.62 | 6.12 | 7 | 8.22 | 7.83 | 5.39 | 6.77 | 3.37 | 5.57 | 7.18
5.7 | 6.89 | 6.95 | 5.33 | 4.44 | 7.44 | 5.57 | 7.99 | 6.72 | 5.85
6.81 | 8.12 | 6.03 | 5.2 | 3.78 | 4.95 | 5.81 | 4.06 | 4.4 | 5.29
6.18 | 5.06 | 7.09 | 4.32 | 6.39 | 5.65 | 5.48 | 6.92 | 4.84 | 7.62
6.59 | 6.74 | 6.48 | 7.32 | 5.05 | 7.75 | 7.66 | 3.98 | 4.87 | 7.34
5.21 | 4.82 | 8.28 | 7.14 | 5.14 | 4.85 | 6.33 | 7.7 | 4.97 | 4.31
7.05 | 5.25 | 5.4 | 4.5 | 5.83 | 4.34 | 6.02 | 5.15 | 5.19 | 4.01
6.39 | 6.92 | 4.8 | 6.72 | 8.41 | 6.17 | 6.58 | 5.96 | 6.67 | 4.71
4.54 | 7.62 | 5.42 | 5.04 | 7.62 | 7.15 | 5.92 | 5.47 | 5.66 | 5.01
7.18 | 4.93 | 4.58 | 5.7 | 5.53 | 6.44 | 8.32 | 5.61 | 5.51 | 7.12
6.69 | 4.76 | 3.69 | 6.99 | 6.33 | 7.68 | 5.66 | 6 | 5.12 | 7.42
5.24 | 7.34 | 6.12 | 5.47 | 6.25 | 7.97 | 5.93 | 6.13 | 4.7 | 6.57
8.38 | 5.46 | 6.01 | 5.57 | 5.25 | 7.2 | 5.32 | 7.4 | 3.51 | 5.64
6.71 | 4.86 | 5.44 | 4.02 | 4.72 | 4.54 | 7.04 | 5.78 | 7.37 | 5.15
4.42 | 5.64 | 5.14 | 5.75 | 6.12 | 4.89 | 7.05 | 6.75 | 8.14 | 5.08
7.73 | 8.07 | 7.19 | 4.85 | 6.92 | 5.82 | 5.37 | 4.44 | 6.18 | 7.04
5.69 | 5.01 | 6.28 | 7.29 | 7.21 | 6.87 | 8.34 | 5.71 | 4.28 | 7.03
4.88 | 5.9 | 5.42 | 3.54 | 4.7 | 7.85 | 6.79 | 6.52 | 7.35 | 4.51
7.49 | 5.62 | 4.57 | 3.7 | 7.05 | 5.87 | 6.55 | 5.97 | 6.08 | 6.54
7.02 | 5.67 | 5.84 | 7.8 | 3.21 | 5.32 | 4.9 | 6.12 | 6.21 | 8.26
5.29 | 7.16 | 5.72 | 4.84 | 6.65 | 5.33 | 3.86 | 4.17 | 4.43 | 5.05
4.61 | 5.7 | 6.02 | 6.48 | 8.53 | 8.39 | 5.3 | 4.39 | 4.65 | 7.94
5.29 | 5.97 | 6.51 | 6.77 | 6.87 | 5.02 | 6.23 | 5.97 | 6.95 | 6.41
6.83 | 7.03 | 5.35 | 4.44 | 8.55 | 3.82 | 4.54 | 5.63 | 4.68 | 5.31
7.69 | 7.11 | 7.11 | 7 | 7.1 | 4.92 | 6.51 | 5.78 | 6.23 | 4.37
5.41 | 4.12 | 5.87 | 7.2 | 4.9 | 5.59 | 5.95 | 5.23 | 6.95 | 6.76
6.88 | 6.41 | 5.49 | 4.89 | 8.63 | 8.15 | 5.06 | 5.2 | 6.03 | 5.83
6.87 | 7.02 | 6.37 | 6.28 | 6.88 | 3.79 | 4.51 | 7.98 | 5.64 | 3.84
6.54 | 6.22 | 5.83 | 7.11 | 5.31 | 6.82 | 6.93 | 5.73 | 6.07 | 6.42
7.31 | 6.86 | 5.77 | 4.64 | 6.76 | 5.19 | 7.68 | 7.1 | 6.71 | 7.91
5 | 6.09 | 5.14 | 6.7 | 6.57 | 7.03 | 5.36 | 6.25 | 6.79 | 6.91
6.32 | 4.63 | 7.75 | 8.55 | 5.19 | 5.77 | 8.75 | 6.17 | 6.35 | 4.98
4.36 | 5.49 | 7.02 | 5.94 | 6.25 | 8.16 | 7.54 | 6.24 | 5.92 | 6.01
7.91 | 7.7 | 5.75 | 7.66 | 5.09 | 5.09 | 7.7 | 5.75 | 4.96 | 6.21
5.26 | 5.16 | 4.55 | 7.17 | 3.91 | 8.35 | 4.97 | 7.35 | 5.84 | 7.64
6.67 | 7.47 | 6.11 | 4.9 | 8.66 | 4.6 | 6.85 | 5.67 | 6.2 | 8.51
5.33 | 5.16 | 3.21 | 5.07 | 3.31 | 5.23 | 6.77 | 5.83 | 5.91 | 4.85
5.09 | 5.93 | 7.23 | 7 | 3.74 | 6.4 | 5.21 | 4.57 | 8.59 | 7.32
6.8 | 7.23 | 5.5 | 5.86 | 6.95 | 5.93 | 5.27 | 6.18 | 7.94 | 5.95
6.22 | 6.84 | 6.16 | 7.53 | 4.81 | 3.31 | 5.99 | 3.96 | 7.47 | 6.41
6.9 | 6.69 | 5.27 | 4.34 | 6.45 | 5.79 | 6.38 | 4.15 | 4.12 | 6.73
5.82 | 6.9 | 6.09 | 8.28 | 8.61 | 6.14 | 7.33 | 7.23 | 3.61 | 8.47
4.87 | 6.66 | 6.44 | 4.16 | 6.8 | 5.46 | 7.5 | 5.72 | 5.17 | 3.45
5.31 | 7.72 | 4.83 | 7.37 | 5.14 | 5.31 | 7.97 | 3.25 | 5.72 | 4.49
5.87 | 7.4 | 4.73 | 5.22 | 7.77 | 7.75 | 4.53 | 7.08 | 7.4 | 8.12
8.1 | 4.23 | 5.31 | 7.77 | 4.77 | 4.81 | 6.45 | 4.69 | 4.32 | 5.7
7.47 | 5.98 | 6.19 | 7.53 | 4.57 | 6.14 | 5.55 | 6.75 | 6.43 | 6.61
3.49 | 7.88 | 4.41 | 5.46 | 5.65 | 5.87 | 5.97 | 7.47 | 6.69 | 7.15
4.69 | 5.66 | 7.32 | 4.71 | 6.77 | 5.17 | 7.85 | 5.29 | 4.28 | 6.66
6.44 | 7.05 | 4.67 | 5.96 | 6.01 | 5.66 | 5.29 | 4.73 | 7.79 | 6.03
5.05 | 3.56 | 6.46 | 6.16 | 7.91 | 6.38 | 7.55 | 6.2 | 5.26 | 5.23
3.69 | 4.48 | 7.17 | 3.89 | 4.2 | 5.38 | 3.7 | 5.26 | 5.84 | 8.07
5.75 | 6.85 | 6.41 | 5.71 | 5.63 | 6.76 | 3.82 | 3.92 | 6.99 | 6.22
6.04 | 8 | 5.95 | 8.03 | 5.47 | 6.25 | 7.36 | 7.85 | 3.88 | 8.49
6.92 | 5.41 | 7.26 | 4.82 | 5.97 | 6.25 | 5.32 | 5.73 | 6.75 | 3.51
6.23 | 7.08 | 7.22 | 6.09 | 5.78 | 4.36 | 7.01 | 5.49 | 5.55 | 5.36
6.16 | 5.38 | 4.84 | 8.66 | 4.39 | 4.39 | 6.34 | 5.11 | 5.8 | 7.02
6.51 | 5.35 | 6.15 | 6.81 | 6.54 | 6.23 | 6.11 | 5.99 | 5.97 | 6.98
7.36 | 7.48 | 6.83 | 5.74 | 7.74 | 6.65 | 4.55 | 5.1 | 4.94 | 6.33
7.26 | 6.68 | 7.07 | 5.06 | 6.04 | 5.06 | 7.44 | 7.07 | 3.79 | 5.46
5.99 | 4.36 | 5.88 | 5.84 | 4.61 | 5.21 | 3.28 | 3.65 | 6.65 | 5.3
8.28 | 7.11 | 8.26 | 6.21 | 5.26 | 3.34 | 5.54 | 4.62 | 7.8 | 5.47
8.55 | 7.58 | 4.28 | 6.96 | 3.43 | 4.48 | 3.88 | 8.12 | 5.97 | 7.45
8 | 6.44 | 6.45 | 5.87 | 5.82 | 6.03 | 7.52 | 6.79 | 6.65 | 6.27
4.31 | 5.55 | 3.39 | 3.78 | 5.52 | 4.37 | 4.92 | 7.62 | 4.53 | 4.17
5.93 | 7.42 | 5.44 | 6.65 | 6.01 | 4.7 | 3.99 | 4.52 | 7.74 | 6.06
5.73 | 7.51 | 4.54 | 4.63 | 8.57 | 4.13 | 5.24 | 7.11 | 3.97 | 5
6.03 | 8.19 | 6.39 | 6.73 | 3.09 | 5.83 | 5.03 | 8.03 | 5.74 | 8.3
6.06 | 5.12 | 7.49 | 7.23 | 6.64 | 4.76 | 7.16 | 6.37 | 8.46 | 6.13
5.58 | 8.18 | 3.72 | 4.4 | 5.85 | 4.55 | 8.18 | 6.86 | 5.83 | 7.38
6.64 | 7.31 | 5.3 | 5.64 | 6.02 | 6.62 | 7.84 | 5.4 | 7.58 | 7.41
8.84 | 5.43 | 7.31 | 7.44 | 6.2 | 5.59 | 7.47 | 6.55 | 5.79 | 5.45
6.15 | 5.44 | 7.93 | 4.23 | 5.52 | 6.66 | 8.55 | 6.24 | 6.42 | 6.24
6.63 | 6.32 | 5.86 | 5.96 | 6.46 | 7.52 | 6.47 | 3.41 | 7.55 | 5.17
7.59 | 5.79 | 5.07 | 8.53 | 8.16 | 7.31 | 7.75 | 8.49 | 6.18 | 5.34
5.17 | 8.15 | 6.28 | 6.61 | 3.99 | 6.4 | 8.39 | 5.55 | 5.1 | 7.66
5.71 | 8.02 | 5.43 | 6.67 | 3.83 | 6.34 | 6.46 | 4.59 | 5.76 | 6.07
5.93 | 5.6 | 5.97 | 5.36 | 3.86 | 6.39 | 4.89 | 6.25 | 6.38 | 4.73
5.47 | 4.5 | 4.66 | 6.37 | 6.42 | 7.61 | 8.21 | 3.78 | 7.15 | 6.16
4.7 | 5.63 | 8.69 | 7.11 | 7.55 | 6.18 | 4.19 | 6.74 | 5.47 | 3.16
5.04 | 6.17 | 6.79 | 6.78 | 6.14 | 6.37 | 6.5 | 6.71 | 6.91 | 5.84
5.66 | 5.08 | 5.09 | 7.18 | 3.68 | 6.33 | 5.22 | 6.73 | 6.06 | 5.78
7.15 | 5.8 | 5.71 | 5.25 | 7.2 | 6.64 | 4.51 | 5.28 | 6.52 | 6.1
5.86 | 4.91 | 7.92 | 6.55 | 6.91 | 8.59 | 5.35 | 5.45 | 3.86 | 5.69
6.62 | 4.37 | 4.96 | 5.44 | 4.87 | 8.41 | 6.08 | 8.61 | 5.57 | 4.98
7.39 | 4.15 | 6.5 | 8.17 | 4.74 | 3.54 | 7.37 | 8.44 | 3.34 | 6.78
6.99 | 6.38 | 7.06 | 6.22 | 5.36 | 5.36 | 6.67 | 4.51 | 6.76 | 5.02
7.17 | 7.04 | 7.79 | 5.76 | 6.32 | 6.55 | 5.83 | 4.29 | 5.56 | 6.03
7.72 | 6.57 | 6.06 | 5.83 | 5.15 | 5.71 | 8.09 | 6.7 | 7.35 | 5.84
5.73 | 5.68 | 4.75 | 5.74 | 4.77 | 7.08 | 5.53 | 5.14 | 6.01 | 7.55
5.55 | 5.2 | 5.39 | 5.6 | 8.22 | 5.25 | 6.77 | 4.91 | 6.6 | 7.83
6.81 | 6.11 | 5.92 | 6.95 | 6.15 | 8.1 | 4.29 | 6.85 | 5.74 | 8.53
5.72 | 4.11 | 5.49 | 5.34 | 6.89 | 6.75 | 5.27 | 4.8 | 6.68 | 6.04
6.03 | 7.17 | 6.66 | 6.42 | 7.38 | 6.9 | 5.14 | 5.3 | 6.89 | 5.57
6.59 | 6.88 | 6.26 | 7.68 | 5.75 | 6.25 | 4.94 | 4.2 | 5.22 | 6.28
4.18 | 6 | 6.09 | 7.47 | 4.99 | 5.67 | 7.11 | 6.06 | 5.49 | 4.81
6.22 | 7.13 | 6.52 | 5.09 | 4.97 | 3.96 | 6.6 | 6.6 | 6.09 | 4.84
6.44 | 4.78 | 3.25 | 5.7 | 4.08 | 6.13 | 6.15 | 7.46 | 5.38 | 6.72
4.88 | 3.95 | 6.87 | 3.98 | 5.76 | 6.62 | 8.13 | 6.11 | 5.42 | 6.11
5.89 | 5.41 | 6.99 | 6.83 | 4.35 | 5.36 | 7.1 | 8.53 | 7.23 | 6.5
4.32 | 5.58 | 8.16 | 4.97 | 6.43 | 6.26 | 5.9 | 5.11 | 7.91 | 5.78
4.03 | 6.2 | 7.11 | 7.31 | 3.56 | 6.51 | 8.22 | 4.9 | 7.95 | 6.28
6.83 | 7.13 | 4.94 | 6.15 | 4.19 | 5.04 | 5.79 | 6.02 | 6.36 | 5.31
8.08 | 6.74 | 6.97 | 4.72 | 4.21 | 5.27 | 4.73 | 5.24 | 5.12 | 4.96
5.38 | 7.95 | 4.25 | 7.98 | 6.03 | 7.12 | 5.14 | 7.65 | 6.61 | 5
7.2 | 6.12 | 6.2 | 5.84 | 5.36 | 6.61 | 3.56 | 6.46 | 6.33 | 6.09
6.37 | 4.73 | 6.85 | 5.23 | 4.34 | 4.85 | 4.88 | 5.38 | 7.87 | 4.62
5.89 | 7.18 | 8.19 | 6.01 | 5.42 | 6.1 | 4.67 | 7.12 | 6.87 | 5.83
7.35 | 6.16 | 5.51 | 4.48 | 7.47 | 8.47 | 7.91 | 8.18 | 6.89 | 4.81
6.45 | 6.38 | 8.39 | 4.39 | 5.3 | 5.4 | 4.81 | 6.07 | 5.52 | 3.82
4.26 | 5.49 | 5.49 | 5.77 | 4.66 | 5.44 | 6.45 | 5.75 | 7.16 | 4.54
6.67 | 5.8 | 4.47 | 6.08 | 4.49 | 6.58 | 6.18 | 6.72 | 7.19 | 5.6
8.44 | 7.06 | 8.08 | 5.95 | 6.14 | 5.84 | 5.29 | 6.18 | 5.77 | 7.76
8.06 | 5.21 | 6.11 | 6.36 | 5.47 | 3.21 | 7.8 | 3.79 | 5.75 | 5.06
7.98 | 6.35 | 6.34 | 4.94 | 6.75 | 3.65 | 6.74 | 7.13 | 5.92 | 4
4.51 | 5.23 | 5.6 | 4.25 | 4.94 | 5.8 | 4.93 | 6.28 | 3.89 | 5.37
3.56 | 5.6 | 7.12 | 5.98 | 6.21 | 8.63 | 5.88 | 7.35 | 5.13 | 5.09
6.16 | 6.83 | 6.62 | 3.28 | 6.58 | 5.2 | 4.99 | 5.61 | 6.4 | 5.65
8.41 | 8.69 | 8.84 | 5.94 | 7.77 | 6.93 | 6.64 | 5.87 | 6.82 | 4.36
7.67 | 6.96 | 4.28 | 6.62 | 6.44 | 3.62 | 6.85 | 5.92 | 5.36 | 8.79
4.92 | 5.56 | 6.64 | 6.36 | 5.21 | 7.07 | 6.42 | 6.44 | 6.41 | 6.13
6.43 | 5.99 | 5.05 | 6.51 | 6.71 | 6.37 | 5.65 | 5.55 | 8.28 | 6.62
5.91 | 5.69 | 5.69 | 6.23 | 7.31 | 3.83 | 6.2 | 5.23 | 5.3 | 7.36
6.34 | 7.63 | 6.41 | 6.34 | 6.13 | 6.56 | 6.18 | 6.4 | 6.98 | 4.39
4.97 | 4.62 | 3.61 | 6.55 | 6.09 | 5.99 | 7.49 | 4.35 | 8.12 | 7.38
5.22 | 6.35 | 8.09 | 5.12 | 5.66 | 7.11 | 6.01 | 7.15 | 5.7 | 4.82
5.63 | 7 | 4.69 | 5.49 | 5.26 | 5.03 | 5 | 6.26 | 5.67 | 7.83
6.79 | 6.14 | 5.74 | 5.97 | 3.87 | 3.69 | 7.22 | 4.28 | 6.1 | 5.18
6.69 | 5.11 | 7.12 | 4.74 | 6.16 | 7.3 | 6.96 | 4.27 | 4.46 | 6.52
5.68 | 4.94 | 5.23 | 5.23 | 6.28 | 6.51 | 4.24 | 7.04 | 5.86 | 4.87
4.9 | 6.42 | 6.13 | 4.95 | 4.78 | 7.32 | 4.76 | 3.68 | 5 | 6.12
6.61 | 6.22 | 6.03 | 5.61 | 3.93 | 6.24 | 6.16 | 4.53 | 8.04 | 5.42
6.48 | 6.95 | 4.98 | 5.13 | 4.32 | 3.99 | 4.23 | 4.64 | 5.9 | 6.07
6.6 | 4.98 | 6.75 | 6.44 | 6.36 | 5.04 | 6.84 | 5.16 | 5.83 | 6.13
4.44 | 4.96 | 7.77 | 5.69 | 6.82 | 6.42 | 6.99 | 8.11 | 5.79 | 7.8
6.51 | 5.1 | 5.34 | 6.06 | 7.88 | 7.49 | 7 | 4.66 | 5.48 | 6.03
4.04 | 7.75 | 5.23 | 6.59 | 5.12 | 5.6 | 8.08 | 7.52 | 5.36 | 6.28
5.6 | 4.93 | 6.42 | 7.34 | 5.8 | 6.64 | 5.31 | 4.76 | 5.69 | 4.69
5.1 | 7.66 | 6.57 | 5.62 | 3.69 | 5.38 | 7.06 | 7.92 | 7.1 | 5.53
6.89 | 6.26 | 4.72 | 5.4 | 7.53 | 4.35 | 7.41 | 7.44 | 4.19 | 5.29
6.04 | 6.36 | 5.93 | 4.28 | 6.06 | 6.8 | 4.25 | 6 | 3.21 | 5.44
4.7 | 7.06 | 6.88 | 6.66 | 5.77 | 3.73 | 6.03 | 4.74 | 5.76 | 4.72
6.47 | 6.79 | 6.63 | 8.07 | 4.36 | 4.5 | 7.11 | 5.07 | 5.59 | 5.4
8.3 | 5.29 | 3.97 | 7.47 | 6.91 | 5.14 | 6.78 | 5.79 | 4.82 | 3.83
7.06 | 6.98 | 6.66 | 6.68 | 4.6 | 6.1 | 4.7 | 4.92 | 3.68 | 6.75
5.51 | 6.21 | 8.79 | 3.58 | 5.4 | 6.07 | 6.52 | 6.42 | 6.16 | 4.97
7.55 | 5.64 | 8.55 | 8.39 | 5.68 | 4.75 | 5.59 | 6.51 | 5.86 | 5.03
5.5 | 7.69 | 5.66 | 7.28 | 6.2 | 5.88 | 7.42 | 3.64 | 7.24 | 5.88
6.91 | 6.69 | 5.98 | 4.98 | 5.27 | 5.66 | 4.11 | 4.65 | 4.57 | 6.41
8.36 | 6.37 | 6.77 | 6.92 | 7.79 | 6.12 | 6.07 | 6.79 | 4.8 | 6.7
6.55 | 7.45 | 6.27 | 6.34 | 5.84 | 7.83 | 8.16 | 6.54 | 6.55 | 3.43
5.95 | 7.44 | 6.62 | 6.21 | 5.53 | 4.8 | 6.86 | 4.79 | 3.75 | 6.2
4.5 | 4.59 | 6.47 | 6.37 | 5.41 | 6.35 | 6.16 | 5.12 | 8.47 | 5.3
6.37 | 6.94 | 7.13 | 6.5 | 5.97 | 4.22 | 8.59 | 6.15 | 6.26 | 7.29
4.48 | 6.37 | 6.59 | 6.45 | 6.34 | 5.89 | 3.16 | 4.75 | 4.82 | 6.63
4.84 | 3.98 | 7.19 | 6.26 | 6.52 | 3.88 | 5.61 | 7.6 | 7.29 | 4.56
7.97 | 5.37 | 6.92 | 6.07 | 6.69 | 6.65 | 4.8 | 6.21 | 4.76 | 6.28
7.68 | 7.35 | 4.48 | 3.76 | 6.85 | 7.13 | 6.39 | 6.98 | 5.85 | 5.74
5.35 | 5.83 | 8.18 | 5.48 | 6.52 | 6.95 | 5.65 | 7.43 | 3.49 | 5.54
3.81 | 5.9 | 6.25 | 5.13 | 6.57 | 6.15 | 6.61 | 5.52 | 4.97 | 3.9
7.52 | 7.31 | 5.33 | 4.17 | 6.25 | 7.04 | 5.59 | 6.12 | 4.89 | 6.49
7.34 | 6.87 | 7 | 6.58 | 7.97 | 8.91 | 6.5 | 6.01 | 6.48 | 6.34
5.96 | 4.48 | 7.03 | 7.93 | 5.24 | 4.88 | 7.32 | 7.7 | 4.31 | 6.84
4.34 | 5.88 | 6.6 | 7.51 | 6.27 | 4.67 | 5.6 | 4.96 | 8.51 | 6.12
6.28 | 5.1 | 6.18 | 5.19 | 6.17 | 5.42 | 4.77 | 6.24 | 6.92 | 5.76
3.31 | 6.55 | 5.56 | 6.91 | 6.4 | 5.3 | 4.62 | 7.38 | 5.64 | 6.53
5.36 | 7.19 | 7.94 | 6.49 | 6.73 | 5.48 | 6.89 | 5.36 | 6.18 | 6.46
3.73 | 5.6 | 5.94 | 6.07 | 5.64 | 5.11 | 6.39 | 3.16 | 6.58 | 4.78
6.68 | 7.2 | 5.64 | 5.82 | 3.25 | 8.44 | 4.7 | 5.8 | 7.58 | 6.59
6.36 | 5.42 | 5.95 | 5.58 | 7.24 | 5.52 | 5.19 | 5.48 | 5.53 | 5.82
6.49 | 5.45 | 5.7 | 5.55 | 6.94 | 4.5 | 7.97 | 6.7 | 4.08 | 4.4
7.33 | 6.15 | 8.14 | 6.25 | 6.71 | 6.45 | 5.74 | 5.53 | 7.84 | 4.24
8.19 | 5.77 | 4.87 | 7.24 | 8.84 | 8.26 | 4.98 | 7.17 | 5.4 | 6.18
6.17 | 4.39 | 6.22 | 6.32 | 5.84 | 7.04 | 7.68 | 5.6 | 8.39 | 5.19
5.95 | 4.68 | 6.77 | 5.32 | 6.86 | 3.43 | 5.76 | 6.03 | 5.89 | 4.28
7.31 | 5.69 | 5.46 | 7.92 | 6.48 | 6.38 | 4.4 | 6.06 | 5.76 | 6.35
6.26 | 4.9 | 5.99 | 4.84 | 6.26 | 6.17 | 6.64 | 7.89 | 6.9 | 7.25
6.79 | 5.36 | 7.97 | 5.96 | 6.99 | 4.74 | 3.43 | 5.5 | 4.58 | 7.74
7.04 | 7.32 | 4.86 | 6.75 | 6.45 | 6.26 | 5.42 | 8.46 | 5.11 | 5.75
6.25 | 4.76 | 6.42 | 7.71 | 5.18 | 6.32 | 5.49 | 5.02 | 6.59 | 4.89
5.43 | 6.93 | 6.7 | 4.45 | 5.28 | 5.72 | 6.08 | 3.91 | 3.25 | 4.66
6.91 | 7.24 | 7.53 | 6.73 | 5.89 | 6.59 | 4.09 | 6.86 | 5.34 | 8.55
6.1 | 8.75 | 3.53 | 6.22 | 4.63 | 3.97 | 6.75 | 6.34 | 6 | 5.91
7.13 | 5.65 | 7.21 | 7.08 | 7.29 | 6.02 | 5.01 | 4.6 | 3.94 | 6.47
4.9 | 7.11 | 5.86 | 5.76 | 5.01 | 7.86 | 5.51 | 8.69 | 7.83 | 6.11
4.17 | 4.38 | 5.63 | 6.23 | 5.39 | 4.9 | 3.68 | 6.67 | 4.69 | 6.99
7.34 | 5.55 | 7.89 | 7.15 | 7.76 | 6.44 | 5.22 | 4.54 | 7.97 | 6.19
7.06 | 6.26 | 6.1 | 8.46 | 4.45 | 5.34 | 6.43 | 7.9 | 5.01 | 7.46
5.19 | 5.69 | 6.17 | 8.32 | 6.97 | 6.16 | 7.87 | 6.46 | 6.66 | 4.09
6.11 | 4.06 | 4.61 | 4.33 | 5.62 | 3.9 | 6.97 | 5.45 | 6.45 | 5.93
7.11 | 7.62 | 4.48 | 7.14 | 8.28 | 8.24 | 3.92 | 5.08 | 3.81 | 5.25
7.8 | 5.01 | 5.1 | 7.61 | 5.85 | 3.09 | 7.24 | 6.19 | 7.68 | 6.96
4.72 | 4.4 | 5.11 | 6.8 | 6.56 | 7.01 | 5.17 | 5.29 | 6.34 | 4.97
5.84 | 6.16 | 4.1 | 7.49 | 6.58 | 7.8 | 5.69 | 7.78 | 7.07 | 7
5.77 | 6.04 | 8.72 | 5.15 | 5.34 | 6.73 | 6.55 | 7.94 | 5.37 | 6.42
5.75 | 5.31 | 4.56 | 5.51 | 6.94 | 7.28 | 5.08 | 5.98 | 5.67 | 8.13
6.65 | 6.24 | 8.03 | 7.33 | 5.38 | 7.6 | 3.31 | 7.38 | 5.63 | 4.7
3.28 | 4.78 | 5.42 | 6.68 | 6.2 | 5.97 | 6.73 | 8.21 | 7.42 | 7.75
5.04 | 6.05 | 7.15 | 7.39 | 5.17 | 5.95 | 6.69 | 4.22 | 5.98 | 6.33
6.95 | 5.71 | 6.34 | 6.25 | 7.12 | 5.76 | 4.72 | 5.56 | 7.33 | 4.9
7.83 | 5.14 | 5.38 | 6.46 | 5.87 | 7.33 | 7.77 | 6.56 | 5.6 | 4.76
5.81 | 6.2 | 7.25 | 5.37 | 6.49 | 5.03 | 7.09 | 4.3 | 4.85 | 7.93
4.73 | 7.77 | 7.53 | 7.69 | 6.39 | 5.72 | 4.42 | 4.32 | 7.15 | 3.21
6.66 | 4.77 | 6.9 | 6.46 | 5.87 | 4.04 | 6.05 | 8.75 | 5.62 | 5.46
5.93 | 7.75 | 5.93 | 6.4 | 6.24 | 7.64 | 6.05 | 4.87 | 7.42 | 7.34
5.15 | 6.19 | 8.57 | 4.85 | 7.23 | 6.08 | 5.84 | 6.77 | 5.89 | 7.14
4.75 | 6.06 | 3.96 | 8.69 | 4.15 | 5.8 | 4.76 | 7.14 | 5.73 | 6.03
6.56 | 6.86 | 6.18 | 4.4 | 4.95 | 6.95 | 6.35 | 8.51 | 4.99 | 5.05
3.43 | 6.13 | 5.47 | 8.01 | 6.43 | 4.77 | 6.14 | 6.69 | 6.83 | 7.16
5.47 | 6.9 | 6.23 | 7.39 | 8.24 | 7.93 | 6.23 | 5.33 | 7.76 | 4.35
6.95 | 6.52 | 3.66 | 4.6 | 5.75 | 8.69 | 5.42 | 5.18 | 6.59 | 5.44
5.74 | 5.29 | 6.24 | 7.13 | 4.58 | 7.87 | 8.12 | 6.84 | 4.9 | 3.89
5.7 | 4.56 | 5.89 | 5.32 | 6.35 | 5.54 | 5.83 | 4.42 | 7.4 | 5.55
6.42 | 4.33 | 5.55 | 3.72 | 6.27 | 6.89 | 6.47 | 3.99 | 7.38 | 4.39
5.92 | 6.08 | 7.99 | 7.22 | 7.78 | 4.88 | 4.62 | 5.34 | 6.44 | 5.08
4.1 | 6.34 | 8.07 | 4.3 | 6.64 | 5.6 | 7.38 | 7.16 | 5.45 | 5.67
4.87 | 5.89 | 5.33 | 4.7 | 5.57 | 5.18 | 5.72 | 6.47 | 7.33 | 5.38
4.8 | 5.09 | 4.65 | 4.86 | 8.02 | 5.21 | 7.92 | 6.88 | 5.28 | 4.91
7.43 | 6.22 | 7.27 | 6.51 | 7.02 | 6.55 | 5.38 | 3.09 | 6.17 | 6.37
6.04 | 7.73 | 6.2 | 3.74 | 6.74 | 5.76 | 5.73 | 6.06 | 8.72 | 5.53
7.55 | 5.04 | 7.38 | 5.43 | 5.99 | 5.06 | 4.46 | 7.83 | 7.08 | 3.34
6.14 | 7.43 | 7.63 | 4.68 | 5.61 | 3.94 | 6.24 | 4.44 | 5.85 | 4.77
7.29 | 5.11 | 6.17 | 8.25 | 5.33 | 3.86 | 5.38 | 3.87 | 6.04 | 6.81
6.27 | 4.61 | 4.32 | 7.62 | 7.92 | 6.02 | 6.53 | 5.84 | 5.97 | 6.43
4.91 | 3.75 | 6.24 | 6.18 | 4.36 | 5.67 | 5.09 | 5.85 | 3.64 | 5.65
6.24 | 6.94 | 5.73 | 5.8 | 4.4 | 7.1 | 7.48 | 8.42 | 5.73 | 5.64
6.89 | 4.28 | 7.1 | 7.56 | 4.09 | 5.45 | 3.21 | 6.49 | 4.32 | 4.92
5.92 | 7.78 | 8.42 | 6.26 | 5.56 | 3.16 | 6.06 | 7.28 | 7.87 | 4.76
5.3 | 7.68 | 8.32 | 6.28 | 5.9 | 5.42 | 5.49 | 4.25 | 5.53 | 6.44
7.53 | 4.84 | 8.41 | 4.27 | 4.71 | 3.47 | 7.18 | 6.37 | 5.5 | 6.52
6.46 | 3.64 | 7.31 | 5.38 | 6.04 | 5.01 | 4.28 | 4.56 | 6.88 | 5.89
4.01 | 5.96 | 6.05 | 6.75 | 6.55 | 6.41 | 6.93 | 6.39 | 6.99 | 6.24
6.06 | 5.26 | 6.42 | 6.2 | 6.18 | 5.09 | 6.13 | 7.77 | 4.93 | 6.62
6.92 | 8.91 | 5.78 | 6.81 | 6.64 | 5.97 | 4.96 | 5.15 | 6.79 | 6.79
4.19 | 6.71 | 7.47 | 4.72 | 6.24 | 4.61 | 4.74 | 4.89 | 6.99 | 6.87
5.67 | 5.61 | 6.43 | 4.45 | 3.59 | 3.51 | 6.68 | 5.77 | 4.42 | 6.19
5.11 | 6.39 | 5.83 | 5.75 | 7.49 | 7.15 | 4.89 | 8.63 | 6.94 | 7.2
6.06 | 6.5 | 6.12 | 5.42 | 5.68 | 8.25 | 7.99 | 8.09 | 5.96 | 5.28
6.38 | 4 | 6.14 | 7.44 | 3.53 | 6.13 | 5.19 | 7.32 | 6.49 | 7.21
7.62 | 4.23 | 7.04 | 6.43 | 6.73 | 3.49 | 6.46 | 4.66 | 6.24 | 4.13
4.06 | 6.7 | 8.44 | 4.91 | 7.34 | 7.34 | 4.05 | 5.84 | 7.72 | 6.22
7.45 | 5.54 | 6.04 | 7.09 | 6.66 | 6.44 | 5.45 | 4.56 | 7.6 | 6.69
7.28 | 6.64 | 7.68 | 6.86 | 5.76 | 7.73 | 5.64 | 7.5 | 5.9 | 7.8
6.25 | 5.56 | 3.37 | 4.57 | 6.66 | 6.46 | 4.31 | 3.39 | 5.43 | 4.75
7.4 | 4.6 | 8.53 | 7.67 | 6.79 | 6.21 | 5.88 | 3.47 | 5.04 | 5.92
4.82 | 5.96 | 3.43 | 5.93 | 8.25 | 4.96 | 5.37 | 4.28 | 6.08 | 7.24
5.84 | 6.79 | 4.23 | 7.17 | 6.95 | 6.59 | 7.28 | 4.38 | 6.56 | 6.87
6.12 | 5.91 | 7.66 | 6.4 | 7.46 | 5.61 | 5.89 | 7.95 | 6.93 | 6.52
5.06 | 7.91 | 6.87 | 7.01 | 8.35 | 6.96 | 6.56 | 4.12 | 5.81 | 5.56
4.83 | 3.8 | 5.65 | 5.94 | 4.76 | 7.23 | 7.76 | 6.99 | 6.88 | 3.28
3.34 | 5.36 | 8.34 | 5.4 | 5.43 | 7.21 | 5.85 | 5.23 | 4.14 | 4.1
6.98 | 6.02 | 6.94 | 7.35 | 7.89 | 6.67 | 6.37 | 8.19 | 4.23 | 6.21
6.48 | 5.71 | 5.16 | 5.7 | 7.81 | 3.84 | 6.57 | 7.05 | 3.62 | 7.7
5.27 | 6.34 | 5.36 | 4.67 | 4.85 | 5.01 | 5.82 | 7.58 | 6.75 | 6.74
6.79 | 7.85 | 6.06 | 4.56 | 7.67 | 4.56 | 6.52 | 6.04 | 4.03 | 5.94
5.98 | 7.39 | 4.52 | 6.5 | 6.32 | 5.84 | 4.79 | 4.94 | 4.56 | 3.87
6.38 | 4.58 | 5.07 | 7.01 | 5.71 | 6.41 | 6.2 | 5.89 | 5.92 | 5.63
6.19 | 6 | 7.4 | 6.42 | 4.12 | 4.44 | 5.1 | 5.42 | 6.32 | 4.89
7.94 | 6.96 | 5.06 | 4.9 | 5.15 | 5.98 | 7.35 | 6.81 | 4.05 | 7.23
6.33 | 4.55 | 5.69 | 5.46 | 6.7 | 7.72 | 8.11 | 4.67 | 4.9 | 4.89
8.91 | 5.54 | 7.44 | 4.46 | 7.49 | 8.22 | 4.78 | 5.86 | 4.94 | 5.53
5.9 | 7.36 | 4.43 | 5.97 | 6.27 | 5.95 | 7.31 | 5.83 | 7.91 | 7.44
4.38 | 6.51 | 5.76 | 4.51 | 4.88 | 8.08 | 3.76 | 8.35 | 4.26 | 5.38
6.84 | 4.31 | 6.69 | 5.28 | 7.68 | 4.27 | 6.11 | 6.54 | 8.49 | 5.08
6.47 | 6.55 | 7.27 | 7.08 | 4.96 | 4.2 | 6.66 | 8.22 | 7.23 | 7.22
5.99 | 5.53 | 4.7 | 6.45 | 4.34 | 6.48 | 7.72 | 4.24 | 4.34 | 5.81
5.61 | 6.15 | 8.2 | 6.16 | 4.83 | 8.34 | 7.57 | 7.13 | 5.91 | 4.88
6.19 | 7.46 | 6.36 | 5.07 | 5.93 | 7.22 | 6.15 | 7.25 | 5.49 | 6.48
5.07 | 6.49 | 7.76 | 5.21 | 7.98 | 6.7 | 4.67 | 7.96 | 6.98 | 5.93
6.81 | 5.84 | 6.41 | 4.91 | 5.57 | 6.01 | 5.34 | 6.21 | 5.3 | 7.86
4.86 | 3.62 | 6.16 | 4 | 6.34 | 6.22 | 6.45 | 6.51 | 7 | 5.66
5.5 | 6.45 | 4.84 | 4.77 | 8.3 | 5.5 | 3.69 | 6.18 | 6 | 5.61
4.53 | 7.49 | 5.15 | 5.45 | 5.83 | 6.88 | 5.76 | 5.56 | 4.79 | 8.72
6.23 | 4.67 | 6.6 | 5.78 | 6.5 | 6.59 | 5.28 | 6.33 | 6.62 | 6.89
6.2 | 6.47 | 7.55 | 6.56 | 6.74 | 7.12 | 5.94 | 6.09 | 4.56 | 6.38
6.01 | 6.22 | 7.83 | 7.25 | 5.98 | 3.75 | 5.25 | 6.17 | 6.82 | 6.23
8.07 | 4.08 | 7.56 | 7.27 | 4.62 | 5.89 | 5.76 | 5.64 | 7.11 | 6.34
5.13 | 5.56 | 5.48 | 6.99 | 8.04 | 6.69 | 5.01 | 3.75 | 7.6 | 5.33
7.01 | 4.45 | 6.11 | 3.61 | 8.27 | 6.55 | 6.84 | 6.88 | 5.44 | 6.37
6.85 | 5.38 | 7.78 | 5.36 | 5.13 | 6 | 7.67 | 6.69 | 7.78 | 8.69
4.46 | 4.45 | 7.04 | 7.78 | 8.79 | 7.11 | 7.1 | 8.41 | 4.2 | 5.34
5.78 | 4.85 | 6.9 | 5.11 | 7.05 | 5.71 | 6.76 | 6.82 | 8.05 | 4.61
6.09 | 6.1 | 7.98 | 6.62 | 6.81 | 5.7 | 6.91 | 6.62 | 3.66 | 7.47
6.35 | 5.57 | 5.01 | 3.87 | 5.28 | 4.02 | 4.78 | 8.28 | 6.46 | 4.63
7.6 | 6.09 | 3.99 | 7.43 | 7.27 | 8.05 | 4.36 | 6.8 | 5.78 | 5.92
6.24 | 8.21 | 8.31 | 6 | 4.2 | 5.32 | 4.83 | 5.92 | 4.95 | 4.64
4.52 | 7.83 | 6.4 | 6.32 | 7.3 | 7.92 | 6.02 | 6.34 | 6.4 | 6.59
7.18 | 4.39 | 4.23 | 6.13 | 7.94 | 8.32 | 6.13 | 5.06 | 7.1 | 6.97
6.11 | 5.75 | 5.93 | 6.02 | 7.33 | 7.77 | 6.72 | 5.27 | 6.64 | 5.61
3.64 | 6.67 | 7.73 | 6.82 | 5.82 | 3.25 | 5.97 | 7.09 | 6.61 | 3.94
7.97 | 4.2 | 4.18 | 7.83 | 7.5 | 6.79 | 7.18 | 7.1 | 6.38 | 7.26
6.41 | 3.66 | 6.13 | 6.53 | 7.35 | 7.19 | 5.49 | 4.82 | 5.99 | 8.84
5.71 | 3.47 | 4.64 | 5.39 | 3.7 | 4.21 | 6.88 | 5.86 | 7.75 | 4.72
3.83 | 8.14 | 6.65 | 5.12 | 4.54 | 4.68 | 4.34 | 4.97 | 4.63 | 4.05
7.84 | 4.4 | 4.13 | 6.74 | 6.16 | 5.88 | 6.49 | 4.98 | 4.88 | 5.14
4.15 | 5.07 | 5.64 | 5.05 | 5.21 | 4.4 | 5.87 | 4.63 | 3.45 | 7.07
6.77 | 3.91 | 5.9 | 5.67 | 6.68 | 5.33 | 5.94 | 6.16 | 7.69 | 7.07
3.93 | 4.38 | 4.77 | 5.63 | 6.61 | 6.52 | 5.8 | 8.04 | 7.44 | 5.49
5.54 | 4.25 | 4.46 | 4.14 | 6.5 | 5.86 | 6.78 | 4.78 | 5.94 | 7.65
5.74 | 5.32 | 6.93 | 4.79 | 6.45 | 7.31 | 5.7 | 6.83 | 6.74 | 7.85
6.63 | 3.28 | 3.85 | 5.41 | 4.17 | 7.19 | 6 | 4.43 | 5.63 | 4.56
6.12 | 4.35 | 7.85 | 6.04 | 3.45 | 4.52 | 7.3 | 5.53 | 3.72 | 7.18
4.32 | 5.15 | 6.58 | 7.79 | 7.14 | 6.04 | 6.35 | 7.02 | 6.12 | 4.03
5.65 | 4.67 | 5.72 | 6.76 | 4.64 | 6.85 | 7.33 | 8.26 | 6.19 | 7.61
5.82 | 7.6 | 7.44 | 4.63 | 6 | 6.27 | 5.8 | 5.38 | 4.83 | 3.25
5.65 | 6.44 | 5.4 | 5.04 | 7.3 | 5.84 | 5.68 | 5.57 | 5.96 | 7.16
6.45 | 3.65 | 6.91 | 4.15 | 5.95 | 8 | 4.35 | 7.8 | 7.52 | 3.66
5.4 | 6.85 | 6.08 | 6.98 | 6.75 | 7.25 | 3.51 | 5.39 | 4.25 | 4.02
4.13 | 3.58 | 6.69 | 4.83 | 5.62 | 5.37 | 5.46 | 5.93 | 6.49 | 6.93
5.72 | 5.3 | 6.68 | 3.81 | 4.67 | 6.47 | 5.02 | 4.37 | 6.26 | 4.7
6.21 | 5.74 | 5.27 | 5.54 | 3.9 | 5.54 | 4.3 | 5.44 | 4.67 | 3.76
5.97 | 6.78 | 8.04 | 5.11 | 3.54 | 7.18 | 5.39 | 3.8 | 7.64 | 5.88
5.37 | 5.44 | 6.71 | 4.32 | 6 | 7.64 | 6.12 | 5.55 | 5.44 | 7.15
6.13 | 5.66 | 5.23 | 7.12 | 5.45 | 6.08 | 5.6 | 5.78 | 6.48 | 3.49
4.66 | 6.28 | 7.86 | 4.36 | 5.51 | 4.24 | 5.41 | 5.72 | 4.8 | 5.11
3.86 | 4.63 | 6.86 | 5.83 | 6.52 | 6.28 | 5.06 | 5.62 | 5.27 | 6.33
5.8 | 7.17 | 5.58 | 6.19 | 5.9 | 4.05 | 5.67 | 5.81 | 6.93 | 8.31
6.5 | 7.27 | 4.85 | 7.99 | 5.72 | 5.22 | 6.2 | 6.69 | 5.62 | 5.68
6.15 | 7.12 | 5.38 | 6.24 | 6.79 | 7.47 | 6.69 | 6.67 | 7.67 | 5.13
6.01 | 4.96 | 8 | 4.87 | 4.55 | 5.51 | 7.42 | 5.97 | 4.98 | 5.69
5.12 | 6.08 | 5.18 | 3.41 | 8.14 | 4.17 | 5.77 | 5.67 | 6.6 | 8.36
4.41 | 4.81 | 7.22 | 6.81 | 6.05 | 7.48 | 4.49 | 7.67 | 5.98 | 6.67
4.51 | 6.75 | 4.94 | 6.61 | 5.81 | 5.36 | 6.56 | 6.78 | 6.39 | 6.73
5.44 | 5.4 | 7.8 | 5.37 | 6.22 | 6.57 | 5.29 | 4.69 | 6.11 | 6.27
4.57 | 8.04 | 4.95 | 7.15 | 5.1 | 4.82 | 5.44 | 5.42 | 7.39 | 7.42
4.65 | 7.33 | 4.79 | 4.17 | 6.1 | 8.07 | 6.83 | 6.95 | 7.04 | 5.48
5.56 | 5.46 | 6.73 | 8.18 | 5.94 | 7.24 | 7.45 | 4.8 | 5.99 | 5.71
4.81 | 6.58 | 6 | 5.53 | 4.47 | 6.43 | 5.21 | 7.61 | 5.21 | 4.3
5.98 | 5.72 | 8.91 | 6.12 | 4.13 | 4.78 | 7.26 | 5.13 | 4.68 | 7.11
4.94 | 7.67 | 5.63 | 7.88 | 4.75 | 3.41 | 5.61 | 6.79 | 5.25 | 5.13
4.59 | 5.62 | 6.61 | 7.32 | 5.58 | 4.66 | 5.54 | 6.23 | 6.23 | 6.45
7.1 | 7.59 | 5.77 | 8.08 | 3.65 | 5.22 | 7.32 | 4.03 | 6.25 | 7.27
4.62 | 5.03 | 5.05 | 6.47 | 4.33 | 5.31 | 4.91 | 5.95 | 5.43 | 5.01
4.09 | 3.16 | 4.3 | 5.19 | 7.86 | 6.48 | 5.02 | 7.77 | 6.86 | 6.79
4.69 | 7.5 | 6.45 | 5.33 | 5.86 | 5.73 | 5.82 | 5.05 | 5.31 | 6.82
5.58 | 5.97 | 7.62 | 6.41 | 6.76 | 5.58 | 6.96 | 5.33 | 6.59 | 5.21
5.96 | 5.93 | 5.17 | 6.64 | 5.83 | 6.04 | 5.26 | 4.48 | 7.7 | 5.11
5.82 | 5.32 | 5.37 | 7.21 | 3.85 | 7.55 | 5.75 | 6.46 | 7.64 | 7.96
6.53 | 5.87 | 7.57 | 6 | 5.51 | 5.73 | 7.26 | 5.04 | 7.73 | 5.77
7.56 | 7.71 | 6.71 | 7.54 | 5.81 | 5.46 | 5.85 | 5.58 | 3.74 | 4.79
6.38 | 5.38 | 8.12 | 5.72 | 5.88 | 4.34 | 7.19 | 7.8 | 5.68 | 8.63
5.16 | 6.27 | 8.27 | 4.01 | 4.25 | 8.17 | 7.4 | 5.74 | 5.56 | 6.34
6.2 | 5.14 | 6.34 | 5.29 | 7.28 | 5.05 | 4.58 | 5.57 | 4.71 | 8.46
3.79 | 6.15 | 5.82 | 4.68 | 6.19 | 4.58 | 5.73 | 7.42 | 4.57 | 8.34
4.94 | 7.4 | 7.61 | 4.75 | 6.37 | 6.21 | 5.53 | 5.09 | 7.05 | 5.12
5.83 | 7.28 | 4.09 | 6.69 | 5.53 | 7.6 | 3.89 | 6.68 | 5.26 | 3.93
8.15 | 7.56 | 4.5 | 8.63 | 5.73 | 7.83 | 6.73 | 8.14 | 7.62 | 4.82
6.77 | 6.17 | 7.95 | 4.52 | 8.69 | 5.88 | 6 | 6.61 | 4.78 | 8.42
6.54 | 3.88 | 5.67 | 6.03 | 5.02 | 7.42 | 3.47 | 4.89 | 4.18 | 6.1
5.64 | 6.38 | 5.2 | 6.35 | 7.34 | 4.71 | 5.41 | 5.99 | 4.84 | 6.14
8.51 | 3.89 | 5.29 | 5.06 | 7.53 | 5.94 | 5.55 | 7.57 | 6.03 | 4.68
5.62 | 6.83 | 5.08 | 5.58 | 4.83 | 6.02 | 3.9 | 6.78 | 4.09 | 5.87
8.66 | 3.86 | 5.61 | 8 | 5.65 | 7.39 | 5.62 | 6.66 | 5.07 | 5.81
7.23 | 5.77 | 5.36 | 8.11 | 4.04 | 4.61 | 7.2 | 4.23 | 5.64 | 5.87
4.53 | 8.22 | 7.81 | 7.07 | 4.61 | 7.4 | 7.78 | 5.13 | 6.02 | 5.42
6.76 | 6.77 | 6.14 | 4.03 | 7.6 | 7.1 | 7.23 | 5.58 | 5.72 | 6.05
5.05 | 4.41 | 7.6 | 5.65 | 5.99 | 6.17 | 5.5 | 6.11 | 6.47 | 7.63
4.35 | 4.87 | 7.03 | 3.8 | 7.03 | 7.05 | 5.61 | 5.44 | 6.94 | 5.14
5.7 | 3.85 | 7.96 | 3.85 | 4.69 | 5.01 | 8.1 | 3.62 | 5.79 | 6.19
7.32 | 6.41 | 8.66 | 5.89 | 6.96 | 6.05 | 6.73 | 4.83 | 4.63 | 7.17
6.92 | 5.48 | 4.82 | 5.68 | 7.68 | 5.92 | 6.64 | 5.46 | 5.74 | 5.75
4.43 | 4.58 | 6.75 | 6.01 | 6.62 | 5.79 | 8.91 | 6.96 | 7.3 | 4.9
4.21 | 6 | 5.7 | 5.39 | 5.83 | 6.87 | 7.14 | 5.36 | 4.44 | 5.95
6.72 | 6 | 5.46 | 4.99 | 5.67 | 4.96 | 5.91 | 6.5 | 7.17 | 5.55
6.93 | 6.11 | 4.12 | 5.54 | 5.87 | 8.31 | 4.66 | 5.94 | 4.13 | 6.63
5.68 | 6.37 | 7.49 | 7.05 | 5.85 | 6.78 | 4.93 | 5.27 | 5.58 | 5.02
5.88 | 4.51 | 4.95 | 8.59 | 6.22 | 4.46 | 5.95 | 7.62 | 8.17 | 7.01
8.79 | 3.99 | 5.21 | 6.02 | 5.06 | 6.09 | 6.27 | 7.87 | 7.2 | 6.58
5.27 | 4.53 | 6.76 | 7.26 | 7.48 | 6.14 | 6.54 | 5.54 | 5.15 | 6.93
3.96 | 7.86 | 4.54 | 7.65 | 6.42 | 6 | 8.79 | 6.4 | 3.87 | 4.45
6.25 | 6.23 | 5.74 | 5.1 | 6.13 | 5.12 | 4.81 | 5.6 | 6.52 | 6.06
6.57 | 4.09 | 6.2 | 5.69 | 5.71 | 4.57 | 5.52 | 5.56 | 6.86 | 6.27
5.86 | 6.14 | 5.01 | 7.16 | 8.18 | 5.2 | 6.71 | 5.79 | 6.66 | 5.56
8.49 | 3.73 | 5.05 | 7.12 | 6.69 | 5.91 | 7.14 | 7.82 | 4.27 | 7.12
4.02 | 7.98 | 4.75 | 5.17 | 5.01 | 7.21 | 8.05 | 6.52 | 6.32 | 5.01
6.32 | 4.46 | 6.02 | 4.78 | 6.24 | 7.46 | 4.98 | 6.63 | 4.55 | 7.5
4.74 | 6.72 | 7.07 | 6.65 | 6.81 | 6 | 7.6 | 3.86 | 7.07 | 6.37
6.09 | 6.63 | 5.01 | 6.06 | 4.65 | 4.7 | 6.44 | 5.46 | 6.55 | 4.99
6.51 | 5.72 | 6.61 | 7.4 | 7.15 | 5.55 | 6.87 | 7.51 | 3.28 | 4.53
5.55 | 6.1 | 6.64 | 6.98 | 5.63 | 7.58 | 7.43 | 7.4 | 6.81 | 6.08
4.25 | 6.63 | 6.54 | 4.49 | 6.51 | 7.47 | 6.57 | 5.59 | 4.3 | 3.72
4.71 | 5.65 | 6.21 | 6.19 | 3.61 | 6.01 | 6.21 | 4.02 | 5.67 | 3.09
3.76 | 4.97 | 5.54 | 6.09 | 3.76 | 6.72 | 6.61 | 5.83 | 7.04 | 7.99
5.9 | 6.05 | 5.77 | 5.54 | 4.93 | 4.89 | 5.35 | 6.28 | 6.25 | 7.82
8.59 | 5.8 | 6.47 | 7.73 | 7.22 | 5.07 | 5.96 | 5.9 | 3.7 | 3.56
4.12 | 7.58 | 3.83 | 5.93 | 6.26 | 5.5 | 5.07 | 4.01 | 4.25 | 5.67
7.48 | 5.81 | 5.89 | 6.58 | 6.54 | 5.08 | 6.05 | 6.71 | 4.06 | 4.67
4.5 | 5.22 | 6.96 | 5.64 | 4.91 | 6 | 5.81 | 5.7 | 5.35 | 5.74
7.04 | 5.3 | 4.45 | 7.18 | 4.18 | 7.71 | 6.17 | 4.41 | 7.61 | 3.85
7 | 6.64 | 5.66 | 7.1 | 3.75 | 5.52 | 5.46 | 5.38 | 4.44 | 5.71
7.87 | 5.54 | 7.18 | 3.31 | 6.69 | 5.16 | 5.96 | 7.49 | 6.92 | 5.88
5.53 | 6.66 | 8.17 | 5.45 | 5.59 | 3.93 | 5.58 | 6.59 | 7 | 4.42
7.08 | 5.27 | 5.74 | 8.34 | 6.19 | 5.45 | 6.75 | 6.76 | 6.05 | 7.11
5.39 | 5.76 | 7.33 | 5.97 | 7.2 | 8.75 | 7.46 | 8.07 | 7.86 | 6.43
5.99 | 7.99 | 7.34 | 5.01 | 7.04 | 7.39 | 7.56 | 6.43 | 5.17 | 5.04
5.52 | 6.24 | 4.66 | 6.03 | 5.3 | 5.54 | 7.39 | 6.58 | 6.11 | 5.19
4.79 | 7.56 | 5.22 | 7.46 | 5.89 | 6.13 | 4.8 | 8.59 | 7.03 | 7.14
6.34 | 4.47 | 7.56 | 4.04 | 4.7 | 7.81 | 7.07 | 6.38 | 7.47 | 4.65
6.5 | 5.95 | 5.56 | 7.37 | 7.27 | 4.3 | 6.87 | 6.48 | 7.31 | 6.56
6.61 | 6.91 | 6.89 | 7.02 | 6.21 | 6.54 | 6.24 | 7.91 | 5.14 | 6.77
5.88 | 4.74 | 4.63 | 5.29 | 6.49 | 7.96 | 4.43 | 4.36 | 4.48 | 5.58
6.6 | 6.81 | 6.81 | 6.27 | 4.75 | 5.55 | 4.84 | 7.49 | 4.81 | 3.54
6.68 | 5.72 | 5.34 | 6.49 | 5.96 | 5.23 | 6.48 | 5.84 | 7.8 | 4.57
8.11 | 6.62 | 7.42 | 3.86 | 6.38 | 6.83 | 5.47 | 6.05 | 8.84 | 6.35
7.37 | 5.84 | 6.18 | 5.35 | 5.55 | 5.82 | 5.78 | 4.6 | 5.39 | 7.04
6.65 | 7.22 | 4.91 | 3.21 | 4.8 | 5.97 | 6.48 | 4.81 | 6.57 | 6.15
5.18 | 7.87 | 6.8 | 4.93 | 6.88 | 4.28 | 7.89 | 6.66 | 6.48 | 4.85
7.16 | 8.05 | 7.42 | 8.14 | 7.38 | 5.96 | 7.55 | 4.58 | 6.41 | 8.03
5.87 | 7.37 | 7.65 | 4.96 | 4.9 | 6.28 | 7.37 | 5.62 | 6.35 | 4.91
5.54 | 4.8 | 3.91 | 5.5 | 5.58 | 6.86 | 8.15 | 4.38 | 7.5 | 4.43
3.45 | 4.9 | 4.96 | 6.47 | 6.22 | 4.43 | 6.41 | 7.39 | 5.34 | 5.35
5.45 | 7.1 | 4.88 | 4.09 | 8.15 | 5.08 | 8.06 | 4.42 | 6.57 | 5.77
4.08 | 7.6 | 7.46 | 5.08 | 4.23 | 7.04 | 7.2 | 6.27 | 5.95 | 6.47
5.06 | 7.68 | 5.38 | 7.27 | 4.22 | 5.77 | 7.35 | 7.08 | 5.4 | 7.33
6.7 | 7.55 | 4.51 | 6.86 | 6.59 | 5.05 | 5.77 | 6.94 | 5.52 | 7.84
5.32 | 5.98 | 6.7 | 6.08 | 7.37 | 6.73 | 6.19 | 5.66 | 5.08 | 7.79
7.89 | 6.03 | 8.25 | 4.82 | 4.92 | 8.66 | 4.02 | 4.09 | 5.89 | 4.23
5.65 | 6.62 | 4.08 | 5.5 | 5.22 | 6.24 | 6.72 | 8.72 | 5.87 | 5.72
7.05 | 3.72 | 7.87 | 4.56 | 8.72 | 6.61 | 7.02 | 5.54 | 5.21 | 6.88
8.24 | 5.97 | 5.61 | 8.84 | 4.24 | 4.47 | 8.3 | 6.13 | 6.36 | 4.61
6.37 | 6.18 | 3.16 | 3.9 | 6.06 | 7.55 | 6.06 | 6.17 | 4.87 | 8.24
5.46 | 7.97 | 5.96 | 5.9 | 5.62 | 6.32 | 7.7 | 5.36 | 6.19 | 5.26
7.62 | 7.97 | 6.78 | 6.48 | 5.66 | 3.61 | 4.84 | 6.09 | 7.19 | 7.39
5.79 | 6.2 | 4.38 | 5.6 | 5.36 | 7.69 | 8.31 | 7.52 | 7.25 | 8.11
4.47 | 7.04 | 5.86 | 4.89 | 5.95 | 5.44 | 4.39 | 7 | 4 | 3.41
7.95 | 5.7 | 5.68 | 5.53 | 5.44 | 6.1 | 6.23 | 8.39 | 5.78 | 6.38
4.79 | 8.38 | 7.72 | 5.16 | 5.39 | 4.06 | 5.93 | 3.53 | 6.41 | 7.11
6.94 | 5.37 | 5.65 | 6.18 | 6.93 | 6.69 | 6.17 | 3.82 | 4.73 | 7.88
6.82 | 6.25 | 7.43 | 5.14 | 5.04 | 7.24 | 5.04 | 5.06 | 5.75 | 5.35
7.1 | 5.2 | 6.88 | 4.54 | 6.79 | 4.51 | 5.9 | 7.22 | 5.82 | 6.06
5.83 | 5.86 | 7.39 | 8.91 | 5.24 | 7.29 | 6.48 | 6.89 | 7.22 | 3.62
5.83 | 7.49 | 4.39 | 4.19 | 7.25 | 6.12 | 5.11 | 5.37 | 7.36 | 5.11
4.99 | 7.76 | 5.45 | 5.1 | 4.53 | 6.52 | 6.28 | 5.69 | 5.75 | 6.67
6.41 | 6.19 | 6.99 | 5.56 | 7.33 | 7.01 | 4.08 | 8.05 | 7.02 | 7.54
3.68 | 5.53 | 7.06 | 8.31 | 7.03 | 6.61 | 6.79 | 6.52 | 5.5 | 6.83
7.12 | 7.37 | 4.27 | 4.21 | 4.82 | 5.76 | 6.89 | 5.03 | 6.63 | 6.02
4.84 | 6.28 | 4.38 | 7.77 | 6.77 | 5.65 | 4.48 | 5.76 | 5.71 | 6.92
6.48 | 5.94 | 5.04 | 6.19 | 4.51 | 7.9 | 5.01 | 4.25 | 5.93 | 7.56
6.82 | 5.19 | 3.58 | 6.27 | 6.6 | 4.31 | 6.86 | 4.03 | 6.5 | 3.39
7.85 | 4.32 | 6.28 | 6.64 | 5.11 | 4.25 | 7.83 | 6.81 | 6.58 | 4.14
4.93 | 6.73 | 7.91 | 5.87 | 5.09 | 4.01 | 3.84 | 6.22 | 6.14 | 6.2
5.81 | 6.42 | 5.64 | 6.95 | 6.72 | 7.14 | 5.86 | 5.08 | 7.96 | 5.01
6.56 | 8.44 | 5.02 | 7.25 | 5.92 | 7.38 | 6.54 | 6.42 | 6.92 | 7.13
5.91 | 5.39 | 6.46 | 4.57 | 5.08 | 4.69 | 5.79 | 7.28 | 6.37 | 3.58
6.07 | 6.6 | 7.5 | 7.55 | 7.72 | 4.51 | 6.53 | 6.66 | 3.92 | 7.55
3.25 | 5.08 | 4.44 | 6.66 | 5.29 | 6.08 | 6.28 | 6.93 | 5.73 | 6.02
6.56 | 6.47 | 6.46 | 5.44 | 5.42 | 7.8 | 6.62 | 4.86 | 4.61 | 4.6
4.3 | 5.87 | 4.98 | 7.95 | 7.4 | 6.38 | 6.51 | 6.99 | 5.65 | 6.75
6.78 | 4.69 | 7.91 | 5.02 | 4.97 | 5.62 | 6.41 | 7.29 | 6.13 | 7.6
6.86 | 8.03 | 7.87 | 6.14 | 5.49 | 4.77 | 7.03 | 5.64 | 4.67 | 8.18
6.78 | 7.8 | 3.62 | 7.6 | 4.26 | 8.72 | 6.98 | 8.32 | 8.22 | 5.41
4.29 | 4.03 | 6.89 | 5.65 | 5.1 | 3.72 | 7.64 | 5.89 | 6.7 | 5.66
7.5 | 7.26 | 3.73 | 5.95 | 5.69 | 5.81 | 7.44 | 5.85 | 6.22 | 5.38
6.57 | 6.43 | 5.27 | 6.15 | 6.03 | 6.82 | 5.51 | 8.57 | 6.62 | 5.44
8.69 | 4.05 | 6.49 | 4.96 | 6.23 | 6.4 | 7.91 | 7.31 | 7.66 | 5.27
6.75 | 6.35 | 6.2 | 6.39 | 5.66 | 5.78 | 5.79 | 6.15 | 5.88 | 4.77
3.85 | 5.39 | 6.54 | 8.27 | 7.41 | 4.99 | 5.23 | 5.35 | 5.29 | 6.67
5.18 | 6.71 | 5.67 | 5.27 | 6.35 | 6.74 | 5.7 | 6.68 | 8.44 | 3.74
4.89 | 5.36 | 6.23 | 7.68 | 5.7 | 6.62 | 6.18 | 8.2 | 5.34 | 6.7
5.2 | 5.03 | 5.61 | 4.66 | 7.56 | 6.27 | 4.45 | 7.09 | 6.52 | 5.58
8.04 | 6.48 | 6.33 | 5.02 | 6.46 | 6.24 | 5.65 | 7.71 | 6.35 | 4.67
5.63 | 5.39 | 7.05 | 4.34 | 5.91 | 8.61 | 3.91 | 8.15 | 3.53 | 4.16
7.27 | 4.85 | 3.7 | 6.84 | 7.42 | 5.58 | 6.92 | 5.46 | 8.38 | 3.37
4.13 | 7.39 | 7.15 | 7.87 | 6.95 | 6.05 | 8.19 | 4.72 | 6.09 | 4.25
6.12 | 4.57 | 8.36 | 7.11 | 4.38 | 7.52 | 4.4 | 6.22 | 6.9 | 5.2
5.37 | 6.76 | 4.76 | 8.38 | 4.5 | 6.39 | 4.95 | 6.38 | 6.2 | 5.9
3.65 | 4.88 | 7.3 | 6.61 | 6.48 | 5.34 | 4.06 | 6.04 | 8.06 | 6.24
4.16 | 7.46 | 5.34 | 6.84 | 5.48 | 5.1 | 4.5 | 8.13 | 5.02 | 4.22
5.62 | 5.42 | 4.35 | 6.24 | 6.61 | 5.57 | 5.89 | 6.1 | 5.41 | 5.5
3.37 | 8.46 | 7.3 | 4.36 | 4.31 | 7.25 | 5.46 | 6.21 | 5.18 | 8.28
5.46 | 5.08 | 5.22 | 6.6 | 7.32 | 6.03 | 5.64 | 4.96 | 6.13 | 5.96
4.65 | 6.4 | 5.68 | 8.12 | 6.4 | 5.27 | 5.23 | 3.74 | 5.68 | 6.78
4.39 | 6.59 | 8.24 | 5.27 | 7.25 | 7.37 | 6.4 | 6.23 | 6.85 | 7.05
7.43 | 5.76 | 3.81 | 6.95 | 4.16 | 3.98 | 6.02 | 5.76 | 6.26 | 5.89
3.74 | 5.57 | 4.42 | 6.04 | 6.83 | 4.45 | 4.61 | 4.53 | 5.38 | 3.81
6.97 | 5.73 | 6.22 | 3.43 | 5.6 | 7.76 | 4.68 | 7.53 | 5.93 | 5.97
7.54 | 4.53 | 6.78 | 5.03 | 6.1 | 5.48 | 5.5 | 5.66 | 4.13 | 3.88
5.5 | 4.18 | 6.95 | 7.97 | 5.78 | 3.7 | 8.07 | 6.91 | 8.16 | 5.57
5.62 | 4.89 | 7.02 | 5.64 | 5.54 | 5.83 | 4.63 | 7.75 | 5.06 | 5.43
8.2 | 5.17 | 3.65 | 5.87 | 4.56 | 5.1 | 5.52 | 6.27 | 5.81 | 5.52
5.33 | 8.79 | 4.31 | 5.59 | 7.07 | 3.66 | 3.73 | 6.62 | 7.21 | 4.13
4.17 | 6.88 | 7.39 | 7.83 | 6.26 | 6.53 | 7.87 | 5.21 | 6.51 | 7.08
6.69 | 8.72 | 5.85 | 6.5 | 8.01 | 5.94 | 5.89 | 3.84 | 4.23 | 5.12
6.75 | 5.83 | 4 | 6.52 | 5.01 | 4.89 | 3.78 | 5.65 | 7.39 | 6.08
6.28 | 6.54 | 3.28 | 6.24 | 6.61 | 7.54 | 6.1 | 4.99 | 6.55 | 6.69
3.92 | 6.45 | 5.82 | 3.84 | 6.63 | 5.77 | 6.08 | 6.1 | 6.74 | 7.08
7.52 | 6.14 | 7.71 | 7.19 | 6.62 | 6.49 | 4.69 | 5.91 | 5.85 | 6.85
5.9 | 6.8 | 7.18 | 7.97 | 7.85 | 7.91 | 6.35 | 7.56 | 4.61 | 5.68
6.05 | 5.31 | 7.6 | 5.89 | 4.8 | 4.48 | 7.11 | 4.63 | 7.21 | 7.27
4.89 | 6.73 | 6.83 | 7.1 | 5.48 | 5.58 | 5.34 | 3.69 | 6.66 | 4.53
5.54 | 7.38 | 6.74 | 5.49 | 3.58 | 4.62 | 3.98 | 3.21 | 5 | 6.59
7.38 | 6.4 | 4.05 | 4.67 | 5.31 | 5.93 | 6.32 | 4.51 | 7.65 | 5.59
6.26 | 4.71 | 5.89 | 6.6 | 6.4 | 5.56 | 5.71 | 6.35 | 5.53 | 5.48
5.57 | 5.59 | 4.76 | 7.91 | 4.28 | 6.98 | 4.82 | 6.83 | 5.24 | 5.16
5.44 | 7.33 | 5.73 | 5.62 | 4.54 | 7.98 | 4.42 | 6.9 | 6.53 | 5.49
6.99 | 5.33 | 6.98 | 4.77 | 4.44 | 5.78 | 3.93 | 6.28 | 5.42 | 5.27
5.11 | 7.19 | 4.62 | 6.13 | 3.97 | 6.83 | 6.61 | 6.89 | 5.39 | 4.87
7.61 | 8.51 | 6.02 | 6.78 | 6.51 | 3.95 | 7.82 | 6.18 | 4.37 | 4.48
7.21 | 6.89 | 4.36 | 6.87 | 7.7 | 7.09 | 6.14 | 4.18 | 3.73 | 8
4.54 | 5.86 | 5.47 | 4.06 | 6.35 | 7.44 | 7.27 | 4.82 | 6.45 | 7.89
5.97 | 4.5 | 4.03 | 4.48 | 6.89 | 6.11 | 5.1 | 5.42 | 5.5 | 6.55
5.44 | 5.05 | 4.6 | 3.91 | 8.06 | 5.87 | 7.79 | 5.18 | 4.73 | 7.28
7.77 | 3.39 | 5.79 | 3.34 | 4.29 | 5.68 | 7.31 | 5.92 | 6.71 | 5.94
6.99 | 5.52 | 7.43 | 4.79 | 6.11 | 3.74 | 4.91 | 4.4 | 6.13 | 4.99
4.2 | 6.13 | 3.76 | 5.69 | 6.55 | 6.08 | 5.83 | 8.55 | 6.64 | 7.58
5.21 | 3.96 | 5.87 | 5.73 | 6.66 | 4.08 | 7.23 | 6.58 | 5.51 | 5.91
4.68 | 5.77 | 4.59 | 5.93 | 7.39 | 4.38 | 5.97 | 7.68 | 4.1 | 4.06
6.07 | 6.86 | 5.08 | 6.09 | 5.55 | 6.23 | 3.95 | 5.41 | 7.71 | 8.44
4.97 | 4.79 | 7.66 | 4.86 | 6.99 | 6.99 | 6.88 | 5.7 | 8.42 | 7.87
5.03 | 5.19 | 6.72 | 5.71 | 5.63 | 5.38 | 6.04 | 5.82 | 7.18 | 8.35
5.27 | 7.15 | 4.88 | 8.75 | 6.07 | 4.03 | 7.75 | 7.64 | 3.98 | 7.22
7.7 | 6.79 | 5.19 | 6.63 | 6.15 | 7.59 | 3.65 | 5.3 | 5.83 | 5.79
6.13 | 7.07 | 5.83 | 5.98 | 3.73 | 6.34 | 7.53 | 4.23 | 5.72 | 5.7
5.76 | 7.91 | 3.75 | 6.73 | 6.12 | 7.72 | 7.25 | 6.2 | 6.83 | 6.4
7.07 | 5.34 | 6.84 | 5.82 | 7.64 | 5.64 | 5.7 | 5.87 | 4.83 | 7.4
5.08 | 6.56 | 7.29 | 6.14 | 8.07 | 5.86 | 4.65 | 7.81 | 6.14 | 8.17
7.02 | 3.51 | 5.25 | 7.36 | 4.13 | 8.02 | 7.5 | 6.01 | 5.08 | 6.99
6.83 | 6.36 | 5.57 | 7.24 | 5.7 | 4.73 | 5.72 | 5.37 | 6.43 | 5.18
6.13 | 4.34 | 5.88 | 5.38 | 5.35 | 8.04 | 8.38 | 5.74 | 4.21 | 6.6
7.33 | 7.81 | 3.41 | 7.2 | 7.04 | 6.46 | 6.99 | 6.35 | 7.11 | 7.48
6.86 | 4.61 | 4.5 | 3.73 | 4.02 | 4.47 | 5.93 | 5.28 | 6.24 | 4.41
5.19 | 3.92 | 4.39 | 5.09 | 6.82 | 6.74 | 7.86 | 6.16 | 7.98 | 4.47
5.15 | 3.09 | 6.62 | 7.04 | 6.77 | 4.13 | 4.16 | 7.44 | 5.99 | 3.96
7.3 | 5.09 | 4.29 | 3.56 | 4.86 | 7.43 | 4.52 | 5.94 | 7.46 | 5.62
5.83 | 3.25 | 6.82 | 5.81 | 5.46 | 6.89 | 5.84 | 6.27 | 4.75 | 6.79
6.05 | 6.76 | 6.55 | 4.53 | 8.08 | 4.92 | 4.54 | 3.85 | 7.97 | 3.92
6.39 | 6.58 | 7.52 | 4.42 | 5.88 | 6.05 | 6.42 | 4.1 | 5.23 | 5.6
6.89 | 7.29 | 6.96 | 6.18 | 6.03 | 5.94 | 5.85 | 4.75 | 5.45 | 6.42
7.81 | 6.99 | 4.63 | 4.69 | 6.15 | 3.68 | 5.4 | 5.63 | 6.76 | 5.24
8.14 | 5 | 7.13 | 8.47 | 8.36 | 5.97 | 6.09 | 7.97 | 5.54 | 5.73
6.73 | 5.5 | 6.25 | 7.64 | 5.96 | 7.68 | 6.46 | 4.96 | 5.61 | 5.98
4.67 | 4.24 | 6.55 | 5.85 | 6.56 | 8.27 | 4.95 | 6.45 | 6.38 | 6.14
5.25 | 7.44 | 8.38 | 5.99 | 6.08 | 5.69 | 4.99 | 4.95 | 5.98 | 7.43
5.6 | 6.97 | 6.56 | 8.2 | 4.43 | 6.19 | 5.25 | 4.93 | 7.49 | 8.32
5.17 | 6.46 | 3.89 | 5.62 | 8.09 | 5.21 | 5.56 | 3.51 | 6.72 | 4.19
5.85 | 5.93 | 5.65 | 5.92 | 6.12 | 7.13 | 7.3 | 7.63 | 5.25 | 4.63
7.46 | 7.52 | 7.14 | 5.26 | 7.24 | 4.87 | 3.34 | 7.3 | 6.23 | 4.8
5.33 | 5.96 | 8.11 | 6.44 | 4.5 | 5.41 | 4.2 | 4.83 | 5.03 | 6.17
5.52 | 6.75 | 8.51 | 7.16 | 6.47 | 4.69 | 7.12 | 6.64 | 5.87 | 6.18
8.34 | 6.16 | 6.84 | 4.23 | 5.03 | 7.18 | 7.28 | 7.16 | 5.69 | 6.15
4.96 | 8.32 | 7.4 | 6.1 | 8.11 | 6.12 | 8.04 | 5.4 | 4.64 | 6.51
5.38 | 7.22 | 5.12 | 3.59 | 5.18 | 5.61 | 4.18 | 4.87 | 6.27 | 6.95
5.43 | 4.97 | 6.12 | 5.14 | 4.69 | 5.52 | 7.43 | 7.45 | 7.01 | 5.07
5.41 | 5.58 | 5.82 | 7.84 | 7.13 | 6.47 | 7.8 | 5.07 | 6.04 | 6.75
3.16 | 5.04 | 4.26 | 6.75 | 6.59 | 5.79 | 5.17 | 5.25 | 6 | 7.64
3.58 | 3.31 | 6.21 | 7.42 | 8.05 | 6.33 | 7.25 | 7.27 | 4.81 | 5.25
4.61 | 7.92 | 5.62 | 5.15 | 6.85 | 5.91 | 6.94 | 4.05 | 7.68 | 6.17
4.63 | 4.66 | 6.4 | 5.45 | 6.16 | 6.12 | 5.4 | 6.22 | 5.96 | 7.05
5.97 | 6.02 | 6.32 | 7.58 | 5.67 | 5.9 | 5.24 | 5.68 | 5.63 | 8.66
7.68 | 3.43 | 6.52 | 6.08 | 5.94 | 6.22 | 4.73 | 4.13 | 5.06 | 6.54
3.66 | 6.21 | 4.78 | 4.24 | 5.79 | 5.61 | 5.68 | 7.21 | 6.86 | 5.76
5.53 | 6.72 | 4.4 | 6.93 | 6.67 | 6.18 | 8.02 | 5.99 | 7.06 | 7.77
8.02 | 6.48 | 5.52 | 5.25 | 6.99 | 5.23 | 6.22 | 5.21 | 4.33 | 5.54
4.44 | 5.34 | 8.61 | 7.63 | 5.07 | 8.13 | 6.33 | 7.86 | 4.38 | 5.99
7.2 | 6.14 | 6.92 | 7.06 | 6.25 | 6.91 | 5.03 | 4.97 | 6.44 | 4.27
6.58 | 6.57 | 4.68 | 7.91 | 5.32 | 4.57 | 6.43 | 5.65 | 5.23 | 5.06
5.64 | 3.69 | 6.07 | 4.76 | 3.49 | 7.4 | 7.05 | 8.84 | 7.43 | 7.26
5.26 | 5.81 | 7.55 | 5.84 | 6.17 | 4.63 | 6.36 | 7.64 | 7.09 | 6.94
7.51 | 4.82 | 4.8 | 6.11 | 7.11 | 6.84 | 5.09 | 5.69 | 6.68 | 6.25
6.67 | 5.61 | 6.03 | 4.96 | 7.51 | 6.6 | 6.65 | 6.08 | 4.35 | 7.19
5.02 | 4.7 | 5.25 | 3.68 | 4.38 | 5.69 | 5.33 | 5.14 | 6.07 | 5.51
8.31 | 6.89 | 8.1 | 5.83 | 6.12 | 8.11 | 4.2 | 7.75 | 6.84 | 7.21
5.08 | 6.99 | 4.71 | 5.31 | 5.5 | 4.8 | 4.79 | 3.28 | 6.5 | 5.32
7.64 | 6.26 | 7.75 | 3.82 | 6.58 | 7.3 | 6.04 | 5.62 | 8.91 | 5.93
5.23 | 5.87 | 4.57 | 6.02 | 6.16 | 4.91 | 6.28 | 6.16 | 5.61 | 6.18
5.67 | 6.28 | 6.35 | 5.8 | 3.94 | 5.75 | 5.92 | 5.52 | 3.59 | 6.83
6.03 | 6.32 | 4.9 | 6.62 | 7.12 | 7.22 | 6.22 | 3.59 | 5.24 | 4.55
6.24 | 3.94 | 7.32 | 3.88 | 5.7 | 7.94 | 6.1 | 5.31 | 6.84 | 5.85
4.76 | 7.24 | 5.52 | 5.58 | 3.64 | 3.87 | 6.74 | 5.74 | 5.62 | 6.08
6 | 5.91 | 6.65 | 4.92 | 3.84 | 8.12 | 4.6 | 6.15 | 5.18 | 7.81
6.55 | 4.47 | 4.09 | 7.05 | 6.1 | 7.91 | 6.26 | 7.5 | 3.39 | 5.8
4.75 | 8.34 | 4.15 | 4.44 | 7.57 | 7.5 | 4.12 | 6.19 | 3.54 | 6.07
4.66 | 6.58 | 6.15 | 6.57 | 5.2 | 8.53 | 6.63 | 5.82 | 7.85 | 6.69
4.05 | 5.76 | 6.37 | 6.23 | 6.97 | 6.84 | 7.21 | 7.69 | 4.92 | 4.8
5.4 | 5.51 | 4.79 | 5.27 | 8.38 | 5.71 | 6.4 | 5.43 | 5.45 | 8.09
6.85 | 7.5 | 6.74 | 6.46 | 6.44 | 5.68 | 5.78 | 4.79 | 6.21 | 7.68
6.28 | 7.05 | 5.39 | 5.42 | 5.82 | 5.29 | 6.21 | 6.97 | 4.6 | 5.97
7.9 | 4.51 | 6.24 | 6.71 | 7.66 | 5.53 | 7.15 | 4.81 | 3.93 | 5.33
5.39 | 5.71 | 3.92 | 5.35 | 6.47 | 4.2 | 3.94 | 5.59 | 5.49 | 4.66
4.99 | 4.14 | 5.97 | 6.72 | 3.82 | 6.42 | 4.44 | 5.04 | 5.41 | 4.46
6.17 | 5.55 | 6.33 | 5.9 | 4.68 | 6.27 | 7.47 | 7.06 | 5.16 | 6.98
4.96 | 5.45 | 6.35 | 4.35 | 5.9 | 5.07 | 4.65 | 7.22 | 5.2 | 5.73
8.63 | 4.42 | 4.4 | 8.04 | 5.99 | 6.36 | 5.2 | 5.02 | 7.63 | 3.79
4.67 | 6.84 | 5.48 | 3.66 | 5.95 | 7.82 | 6.59 | 6.47 | 7.32 | 7.9
4.6 | 4.74 | 6.21 | 6.48 | 5.72 | 6.5 | 6.32 | 7.58 | 4.11 | 3.98
6.05 | 3.34 | 6.83 | 6.06 | 5.44 | 6.04 | 4.87 | 4.58 | 5.11 | 7.73
5.07 | 5.82 | 6.47 | 5.44 | 3.95 | 4.93 | 5.74 | 5.63 | 6.85 | 6.01
5.19 | 7.32 | 6.17 | 5.72 | 8.46 | 3.78 | 6.9 | 4.73 | 5.85 | 5.8
7.96 | 5.85 | 7.2 | 7.22 | 4.89 | 6.75 | 6.82 | 6.56 | 7.81 | 6
4.49 | 8.49 | 5.5 | 6.26 | 5.86 | 5.11 | 4.57 | 5.2 | 6.03 | 6.72
5.67 | 6.33 | 7.35 | 5.91 | 5.98 | 8.3 | 8.35 | 5.29 | 4.99 | 7.1
3.59 | 6.05 | 4.49 | 5.25 | 5.31 | 6.67 | 5.26 | 5.41 | 7.14 | 6.97
7.44 | 4.65 | 3.54 | 4.38 | 4.11 | 5.91 | 5.05 | 6.27 | 7.77 | 5.31
4.23 | 4.57 | 4.89 | 4.89 | 7.97 | 6.71 | 6.05 | 6.64 | 7.92 | 7.44
6.86 | 3.45 | 3.64 | 5.82 | 7.16 | 6.47 | 5.68 | 6.14 | 4.91 | 6.64
7.15 | 7.03 | 7.24 | 7.21 | 4.05 | 5.96 | 5.63 | 7.19 | 6.8 | 6.32
5.21 | 7.9 | 5.51 | 7.09 | 4.42 | 7.11 | 7.72 | 7.37 | 7.59 | 4.2
5.46 | 6.04 | 7.35 | 6.12 | 6.51 | 5.29 | 6.07 | 6.48 | 7.2 | 5.05
4.83 | 5.28 | 7.25 | 6.89 | 7.06 | 7.45 | 6.52 | 7.03 | 6.05 | 6.92
5.76 | 6.68 | 6.28 | 4.75 | 4.68 | 6.97 | 3.8 | 8.06 | 5.35 | 4.2
7.6 | 8.53 | 6.18 | 6.04 | 5.23 | 6.46 | 5.86 | 6.26 | 3.95 | 5.67
6.34 | 6.08 | 5.35 | 5.81 | 5.56 | 6.86 | 5.93 | 3.97 | 6.05 | 3.59
4.34 | 7.57 | 5.28 | 8.51 | 5.86 | 8.06 | 6.55 | 3.88 | 5.55 | 4.59
4.72 | 5.25 | 5.78 | 8.02 | 5.93 | 4.78 | 3.41 | 7.79 | 8.31 | 4.45
5.1 | 7.66 | 6.19 | 5.29 | 5.41 | 5.26 | 5.91 | 8.36 | 8.07 | 6.61
4.76 | 4.2 | 3.74 | 6.47 | 6.05 | 6.48 | 5.57 | 7.93 | 6.03 | 4.6
8.75 | 6.53 | 3.49 | 6.27 | 4.46 | 4.95 | 5.63 | 5.14 | 5.65 | 4.34
6.58 | 6.25 | 4.58 | 4.61 | 7.55 | 7.26 | 7.38 | 5.91 | 6.71 | 4.93
4.77 | 4.19 | 4.92 | 5.78 | 7.64 | 6.06 | 5.15 | 6.08 | 6.95 | 3.73
7.83 | 8.57 | 5.6 | 8.19 | 7.09 | 6.91 | 6.81 | 3.94 | 7.13 | 6.09
5.64 | 8.16 | 5.97 | 6.51 | 7.96 | 6.24 | 6.91 | 7.91 | 3.69 | 3.68
6.4 | 6.06 | 6.14 | 8.57 | 3.41 | 5.28 | 8.51 | 5.87 | 8.75 | 3.64
7.7 | 5.48 | 5.9 | 4.28 | 6.47 | 7.35 | 7.15 | 5.33 | 5.65 | 6.32
4.27 | 5.24 | 3.47 | 7.03 | 5.29 | 4.67 | 5.54 | 5.03 | 5.46 | 6.22
4.38 | 7.41 | 4.34 | 5.77 | 6.1 | 4.39 | 4.71 | 5.88 | 8.25 | 6.55
6.52 | 6.77 | 5.84 | 7.8 | 7.01 | 4.72 | 6.56 | 6.87 | 7.44 | 5.4
6.25 | 6.17 | 4.61 | 4.74 | 4.94 | 5.69 | 5.96 | 6.56 | 8.15 | 7.72
8.12 | 5.33 | 6.95 | 5.3 | 6.8 | 4.83 | 5.73 | 6.62 | 5.58 | 6.48
6.88 | 6.62 | 7.64 | 3.94 | 8.51 | 6.96 | 4.87 | 5.95 | 3.91 | 6.86
6.15 | 7.38 | 6.38 | 6.97 | 4.98 | 6.77 | 4.45 | 6.86 | 6.04 | 5.21
7.19 | 6.5 | 4.11 | 4.43 | 6.23 | 6.6 | 5.39 | 6.36 | 6.27 | 7.37
5.85 | 8.06 | 5.06 | 5.11 | 7.42 | 5.85 | 6.67 | 4.08 | 5.87 | 5.56
3.47 | 5.42 | 4.14 | 7.72 | 5.69 | 4.36 | 6.09 | 6.03 | 5.32 | 4.78
7.25 | 7.74 | 6.48 | 4.65 | 5.77 | 6.18 | 4.41 | 8.25 | 3.83 | 7.58
6.22 | 4.68 | 6.98 | 5.76 | 6.38 | 6.49 | 3.53 | 7.88 | 6.91 | 5.75
4.81 | 7.47 | 7.7 | 8.16 | 4.1 | 4.66 | 4.25 | 5.66 | 5.09 | 6.05
5.38 | 5.06 | 5.59 | 8.24 | 4.53 | 6.5 | 7.64 | 5.77 | 8.11 | 7.03
5.45 | 4.17 | 6.57 | 3.45 | 4.79 | 5.99 | 8.72 | 7.37 | 6.46 | 8.38
7.03 | 4.86 | 5.58 | 4.95 | 8.19 | 6.41 | 6.37 | 3.95 | 6.62 | 5.51
5.17 | 6.46 | 6.13 | 4.8 | 5.2 | 6.56 | 6.44 | 4.54 | 6.54 | 5.45
5.29 | 6.71 | 5.8 | 6.05 | 5.64 | 7.67 | 8.25 | 7.66 | 5.7 | 6.35
4.45 | 7.12 | 8.47 | 6.59 | 6.93 | 6.85 | 4.23 | 7.31 | 6.06 | 6.26
6.27 | 5.46 | 5.62 | 7.75 | 5.04 | 4.93 | 5.8 | 5.69 | 4.36 | 5.79
6.16 | 6.65 | 7.08 | 6.96 | 3.66 | 5.16 | 4.75 | 4.11 | 4.88 | 8.01
4.82 | 6.83 | 4.97 | 6.93 | 5.33 | 5.8 | 5.15 | 6.72 | 5.95 | 3.78
5.48 | 5.7 | 5.46 | 5.98 | 7.02 | 5.55 | 4.66 | 7.06 | 6.25 | 7.53
4.42 | 7.2 | 3.95 | 7.3 | 6.44 | 7.08 | 4.32 | 7.11 | 5.22 | 7.78
5.78 | 6.18 | 5.9 | 5.18 | 6.11 | 6.51 | 6.92 | 7.56 | 6.96 | 5.22
3.51 | 8.11 | 7.8 | 5.5 | 5.74 | 6.86 | 5.42 | 6.02 | 6.54 | 4.86
4.23 | 7.84 | 5.98 | 7.48 | 4.73 | 4.75 | 7.03 | 5.11 | 6.97 | 5.9
6 | 7.28 | 6.05 | 7.9 | 4.03 | 3.39 | 4.22 | 7.23 | 5.41 | 4.12
5.36 | 5.82 | 6.73 | 8.36 | 4.62 | 7.84 | 7.83 | 5.97 | 7.27 | 4.88
5.92 | 6.19 | 5.17 | 5.34 | 7.09 | 5.89 | 7.63 | 4.71 | 4.41 | 7.32
5.98 | 7.02 | 5.11 | 3.16 | 6.71 | 8.28 | 5.33 | 6.94 | 5.2 | 5.41
3.95 | 6.21 | 6.54 | 6.05 | 5.92 | 6.1 | 6.16 | 6.73 | 7.5 | 6.8
5.77 | 5.13 | 6.24 | 7.6 | 6.92 | 4.03 | 3.75 | 3.66 | 6.56 | 5.55
4.98 | 5.61 | 6.94 | 5.01 | 4.84 | 4.63 | 4.5 | 4.72 | 4.17 | 5.91
7.28 | 6.7 | 6.53 | 6.2 | 5.38 | 5.5 | 5.87 | 6.11 | 4.04 | 7.06
7.11 | 6.23 | 5.79 | 6.28 | 6.08 | 6.63 | 6.99 | 6.32 | 4.66 | 4.58
7.44 | 8.08 | 5.91 | 6.89 | 6.9 | 4.09 | 5.69 | 6.13 | 5.69 | 5.83
4.11 | 3.97 | 6.39 | 4.26 | 4.52 | 7.66 | 5.47 | 4.34 | 4.72 | 5.16
8.21 | 5.79 | 6.49 | 4.93 | 6.83 | 4.09 | 5.33 | 6.57 | 7.51 | 4.93
5.56 | 5.45 | 7.21 | 4.94 | 3.92 | 4.53 | 5.98 | 6.89 | 4.34 | 5.97
7.64 | 6.16 | 7.54 | 7.26 | 7.43 | 7.88 | 8.41 | 6.07 | 6.25 | 4.36
7.24 | 6.13 | 6 | 7.56 | 5.14 | 5.27 | 6.66 | 6.73 | 6.28 | 6.22
5.52 | 5.92 | 6.5 | 5.66 | 7.7 | 5.31 | 4.36 | 5.61 | 6.06 | 8.27
7.42 | 7.01 | 5.97 | 4.11 | 6.2 | 4.44 | 8.63 | 7.74 | 7.14 | 5.37
7.76 | 5.95 | 6.81 | 7.49 | 5.74 | 7.2 | 5.75 | 6.33 | 7.03 | 6.76
7.27 | 3.9 | 6.14 | 5.51 | 5.44 | 6.16 | 5.91 | 6.59 | 6.73 | 6.23
4.85 | 7.07 | 7.5 | 4.81 | 4.14 | 5.28 | 5.07 | 4.78 | 4.58 | 6.36
6.02 | 4.54 | 7.47 | 6.11 | 6.03 | 7.95 | 5.48 | 4.55 | 4.24 | 3.7
6.26 | 5.22 | 3.84 | 6.44 | 6.78 | 5.9 | 4.83 | 7.26 | 6.17 | 5.39
5.89 | 5.85 | 6.05 | 6.05 | 7.8 | 5.34 | 5.11 | 5.34 | 4.51 | 6.92
6.66 | 5.78 | 6.89 | 5.66 | 7.11 | 6.9 | 4.13 | 4.61 | 4.49 | 4.84
5.08 | 7.8 | 5.41 | 6.07 | 5.84 | 6.06 | 6.14 | 5.48 | 8.3 | 6.44
6.52 | 5.86 | 4.45 | 5.49 | 6.13 | 6.83 | 5.75 | 8.66 | 7.38 | 5.45
4.4 | 6.48 | 5.92 | 6.74 | 6.89 | 4.74 | 3.85 | 3.73 | 8 | 6.12
8.18 | 4.28 | 4.47 | 6.12 | 3.8 | 5.53 | 6.1 | 6.25 | 6.22 | 4.75
3.9 | 3.79 | 6.8 | 8.79 | 8.44 | 3.56 | 4.63 | 8.1 | 4.72 | 4.69
5.22 | 5.48 | 5.33 | 6.11 | 6.07 | 4.79 | 5.04 | 5.51 | 6.11 | 6.14
7.77 | 4.69 | 6.67 | 8.1 | 6.02 | 6.93 | 7.62 | 8.3 | 8.36 | 5.36
4.24 | 4.66 | 5.03 | 5.73 | 7 | 6.36 | 6.62 | 5.81 | 4.4 | 7.17
7.78 | 6.24 | 5.17 | 5.59 | 6.83 | 4.64 | 5.94 | 5.85 | 4.16 | 4.95
8.57 | 6.92 | 8.49 | 3.47 | 4.06 | 5.93 | 4.61 | 5.9 | 5.36 | 7.59
7.41 | 8.66 | 5.59 | 3.25 | 6.41 | 8.84 | 3.72 | 4.31 | 7.9 | 7.75
5.23 | 5.26 | 6.58 | 6.54 | 6.84 | 4.96 | 6.97 | 7.25 | 5.13 | 6.64
6.02 | 7.16 | 5.37 | 5.85 | 5.45 | 5.64 | 6.12 | 3.49 | 5.33 | 5.96
7.09 | 3.83 | 6.06 | 8.41 | 7.59 | 6.56 | 5.27 | 5.17 | 6.05 | 6.36
6.73 | 6.97 | 6.58 | 6.85 | 5.08 | 7.03 | 6.65 | 6.95 | 5.27 | 6.18
3.53 | 5.83 | 5.93 | 6.1 | 7.47 | 5.13 | 6.09 | 6.33 | 6.18 | 6
3.39 | 7.09 | 5.62 | 5.46 | 5.25 | 6.01 | 6.14 | 7.18 | 5.93 | 4.42
6.84 | 6.01 | 5.44 | 8.26 | 5.64 | 7.42 | 3.66 | 7.83 | 6.53 | 8.57
7.37 | 5.95 | 6.75 | 3.79 | 5.6 | 5.24 | 6.06 | 6.99 | 7.02 | 7.09
6.11 | 6.81 | 4.86 | 5.91 | 4.82 | 4.41 | 3.45 | 5.39 | 5.33 | 5.49
5.95 | 6.1 | 5.88 | 5.36 | 5.59 | 6.35 | 6.95 | 6.61 | 8.57 | 8.19
7.19 | 5.66 | 6.55 | 4.38 | 7.8 | 4.58 | 5.99 | 6.83 | 6.15 | 6.44
5.24 | 5.9 | 6.48 | 5.16 | 4.45 | 7.79 | 7.06 | 6.91 | 7.46 | 7.01
7.32 | 4.27 | 4.73 | 6.38 | 6.06 | 5.82 | 3.54 | 6.43 | 6 | 7.33
6.46 | 4.29 | 5.91 | 6.38 | 6.28 | 5.49 | 5.53 | 5.88 | 6.1 | 6.94
6.5 | 8.36 | 6.67 | 6.9 | 8.34 | 8.49 | 5.18 | 5.5 | 5.01 | 6.04
5.68 | 4.22 | 4.97 | 4.73 | 6.07 | 5.92 | 4.85 | 6.6 | 5.59 | 5.93
4.8 | 7.23 | 6.59 | 5.79 | 7.87 | 4.42 | 5.44 | 7.32 | 7.05 | 5.15
5.13 | 5.27 | 5.78 | 5.92 | 8.32 | 6.27 | 6.71 | 5.31 | 8.18 | 6.26
5.49 | 6.23 | 4.96 | 5.83 | 6.53 | 4.98 | 4.92 | 3.7 | 8.01 | 6.73
5.35 | 5.47 | 5.73 | 6.53 | 5.85 | 5.63 | 5.58 | 5.34 | 5.54 | 6.16
7.87 | 8.55 | 7.24 | 5.65 | 4.59 | 6.25 | 6.76 | 6.24 | 4.2 | 5.74
7.08 | 4.02 | 6.43 | 5.41 | 7.9 | 6.42 | 6.49 | 4.32 | 6.12 | 8.59
7.49 | 4.09 | 6.71 | 3.49 | 5.8 | 7.89 | 4.27 | 5.58 | 5.11 | 5.62
8.01 | 7.55 | 5.08 | 4.31 | 4.79 | 4.54 | 4.82 | 4.16 | 5.46 | 5.61
5.16 | 4.52 | 6.48 | 7.3 | 5 | 6.79 | 5.62 | 5 | 5.04 | 5.99
7.04 | 6.42 | 7.41 | 5.52 | 6.18 | 5.75 | 6.37 | 7.14 | 8.61 | 7.98
5.76 | 5.18 | 4.89 | 4.39 | 6.46 | 4.72 | 6.15 | 3.45 | 3.43 | 6.15
6.41 | 7.79 | 7.37 | 6.17 | 5.33 | 7.74 | 8.53 | 5.72 | 6.19 | 5.09
5.48 | 4.6 | 8.21 | 5.31 | 4.6 | 6.28 | 5.71 | 5.43 | 4.17 | 3.8
6.14 | 5.43 | 7.14 | 6 | 6.48 | 7.66 | 7.29 | 5.01 | 5.55 | 8.21
7.75 | 5.99 | 6.01 | 7.19 | 5.11 | 4.23 | 7.17 | 3.61 | 3.56 | 5.2
6.2 | 5.23 | 7.2 | 7.7 | 6.37 | 5.29 | 7.52 | 4.85 | 8.32 | 5.36
4.56 | 6.91 | 6.5 | 7.7 | 4.03 | 7.7 | 4.68 | 6.25 | 8.66 | 6
4.36 | 3.74 | 4.74 | 5.93 | 6.08 | 3.85 | 8.61 | 7.21 | 5.6 | 5.86
6.16 | 6.51 | 7.38 | 6.79 | 5.49 | 4.16 | 4.75 | 5.64 | 7.09 | 8.75
4.09 | 4.32 | 6.77 | 4.58 | 7.26 | 3.28 | 6.19 | 4.49 | 4.38 | 7.52
7.23 | 8.35 | 5.24 | 5.85 | 4.65 | 8.42 | 4.17 | 4.98 | 7.72 | 5.81
4.73 | 6.18 | 7.33 | 5.86 | 5.67 | 7.09 | 5.11 | 7.73 | 6.42 | 6.5
4.78 | 5.02 | 6.92 | 7.23 | 5.46 | 6.77 | 6.42 | 7.27 | 6.16 | 6.04
7.71 | 4.56 | 7.46 | 5.38 | 5.05 | 4.65 | 3.62 | 5.93 | 4.42 | 4.94
5.79 | 7.25 | 7.48 | 6.54 | 6 | 8.03 | 3.81 | 6.92 | 7.08 | 5.21
5.94 | 6.03 | 7.17 | 7.38 | 6.84 | 7.49 | 4.34 | 5.91 | 5.05 | 4.68
4.92 | 4.44 | 5.28 | 5.17 | 4.88 | 4.12 | 4.17 | 5.01 | 4.69 | 7.3
4.64 | 3.93 | 8.02 | 6.27 | 7.87 | 4.19 | 7 | 5.9 | 6.24 | 6.58
5.14 | 7.93 | 3.86 | 3.96 | 8.47 | 6.28 | 6.03 | 6.44 | 5.48 | 8.41
6.96 | 6.69 | 7.16 | 4.7 | 5.97 | 4.23 | 6 | 4.84 | 6.01 | 8.16
4.6 | 6.03 | 7.67 | 7.58 | 6.05 | 5.24 | 7.96 | 7.47 | 8.2 | 6.71
5.09 | 3.81 | 4.19 | 8.05 | 8.42 | 3.53 | 5.19 | 6.41 | 8.02 | 4.5
4.58 | 5.75 | 4.25 | 6.97 | 6.28 | 6.81 | 6.5 | 6.23 | 6.79 | 5.77
4.78 | 8.59 | 4.56 | 4.51 | 4.91 | 6.05 | 3.87 | 5.59 | 7.12 | 7.91
7.66 | 4.88 | 7.58 | 3.75 | 7.93 | 8.46 | 5.84 | 6.05 | 6.34 | 5.96
6.18 | 3.7 | 6.59 | 8.44 | 7.13 | 5.47 | 6.2 | 5.96 | 4.39 | 5.23
5.74 | 3.87 | 4.16 | 5.3 | 7.6 | 6.92 | 7.74 | 5.01 | 4.47 | 3.75
7.63 | 6.56 | 3.56 | 5.95 | 7.58 | 5.56 | 3.59 | 4.26 | 6.78 | 5.23
5.59 | 8.2 | 6.61 | 5 | 5.08 | 7.58 | 4.56 | 6.98 | 3.99 | 5.85
6.48 | 4.34 | 6.16 | 5.48 | 6.28 | 4.76 | 4.72 | 5.19 | 5.77 | 5.72
5.85 | 8.31 | 7.08 | 5.88 | 5.92 | 5.74 | 7.13 | 5.27 | 6.1 | 6.1
4.68 | 7.26 | 3.09 | 5.61 | 6.38 | 3.45 | 5.58 | 5.81 | 4.96 | 5.22
8.53 | 6.59 | 7.97 | 4.76 | 3.88 | 8.57 | 5.13 | 4.33 | 5.83 | 6.64
3.84 | 6.27 | 6.22 | 6.56 | 3.98 | 5.39 | 6.03 | 7.04 | 3.31 | 7.23
5.86 | 7.18 | 3.68 | 6.14 | 4.27 | 7.43 | 8.66 | 4.89 | 6.2 | 7.24
4.39 | 5.92 | 5.24 | 6.63 | 5.12 | 3.59 | 7.4 | 7.97 | 6.21 | 5.86
5.01 | 6.99 | 7.23 | 3.51 | 5.49 | 5.73 | 7.71 | 4.09 | 7.01 | 6.96
8.25 | 3.49 | 6.33 | 5.88 | 5.54 | 6.09 | 6.24 | 6.76 | 8.41 | 5.68
6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91
0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582
3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09
3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672
4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254
4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836
5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418
6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582
7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164
7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746
8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062
0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099
0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138
0.175 | 0.175 | 0.175 | 0.174 | 0.175 | 0.175 | 0.175 | 0.174 | 0.174 | 0.174
0.178 | 0.178 | 0.178 | 0.179 | 0.178 | 0.178 | 0.178 | 0.179 | 0.179 | 0.179
0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137
0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099
0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087
0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186
0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324
0.499 | 0.499 | 0.499 | 0.498 | 0.499 | 0.499 | 0.499 | 0.498 | 0.498 | 0.498
0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677
0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814
0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913
0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976
1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001

## PMTable
20 | Generated with the SIPmath™ Modeling Tools from ProbabilityManagement.org
| Index | Released
| Values | 7.66
| 1 | 7.68 | To learn more about the open SIPmath standard visit |  | http://www.probabilitymanagement.org/Sipmath.htm
| 2 | 7.82
| 3 | 7.05 | For an article in Analytics Magazine visit | http://viewer.zmags.com/publication/90ffcc6b#/90ffcc6b/29
| 4 | 7.77
| 5 | 7.53
| 6 | 7.96
| 7 | 7.26
| 8 | 7.83
| 9 | 7.2
| 10 | 6.7
| 11 | 7.79
| 12 | 7.57
| 13 | 8.22
| 14 | 6.71
| 15 | 8.79
| 16 | 7.63
| 17 | 7.84
| 18 | 8.2
| 19 | 8.31
| 20 | 7.66
| 21 | 8.36
| 22 | 7.6
| 23 | 8
| 24 | 7.95
| 25 | 7.59
| 26 | 7.57
| 27 | 8.08
| 28 | 6.77
| 29 | 6.09
| 30 | 8.22
| 31 | 7.99
| 32 | 7.74
| 33 | 8.55
| 34 | 7.75
| 35 | 8.1
| 36 | 7.02
| 37 | 7.14
| 38 | 8.08
| 39 | 8.61
| 40 | 7.43
| 41 | 8.2
| 42 | 7.34
| 43 | 8.17
| 44 | 7.88
| 45 | 8.17
| 46 | 8.59
| 47 | 7
| 48 | 8.01
| 49 | 7.52
| 50 | 6.67
| 51 | 8.21
| 52 | 7.73
| 53 | 7.58
| 54 | 8.16
| 55 | 8.13
| 56 | 7.94
| 57 | 7.84
| 58 | 7.08
| 59 | 8.27
| 60 | 8.17
| 61 | 7.21
| 62 | 7.87
| 63 | 8.09
| 64 | 7.53
| 65 | 7.31
| 66 | 8.75
| 67 | 7.52
| 68 | 7.72
| 69 | 8.63
| 70 | 7.37
| 71 | 7.75
| 72 | 6.21
| 73 | 6.61
| 74 | 8.61
| 75 | 8.02
| 76 | 8.32
| 77 | 8.84
| 78 | 8.22
| 79 | 7.51
| 80 | 8.03
| 81 | 8.84
| 82 | 8.03
| 83 | 6.36
| 84 | 8.27
| 85 | 6.88
| 86 | 8
| 87 | 7.89
| 88 | 7.42
| 89 | 7.6
| 90 | 7.52
| 91 | 7.4
| 92 | 7.8
| 93 | 8.2
| 94 | 8.38
| 95 | 8.21
| 96 | 8.61
| 97 | 8.13
| 98 | 8.34
| 99 | 6.51
| 100 | 7.99
| 101 | 8.13
| 102 | 7.82
| 103 | 6.82
| 104 | 7.35
| 105 | 8.28
| 106 | 6.95
| 107 | 8.42
| 108 | 7.81
| 109 | 7.35
| 110 | 7.77
| 111 | 8.3
| 112 | 8.26
| 113 | 8.02
| 114 | 8.05
| 115 | 6.73
| 116 | 7.72
| 117 | 7.65
| 118 | 7.89
| 119 | 8.55
| 120 | 7.95
| 121 | 8.35
| 122 | 6.38
| 123 | 8.27
| 124 | 8.03
| 125 | 7.14
| 126 | 8.39
| 127 | 8.63
| 128 | 8.91
| 129 | 7.39
| 130 | 8.35
| 131 | 7.87
| 132 | 7.32
| 133 | 8.46
| 134 | 7.72
| 135 | 7.82
| 136 | 7.68
| 137 | 7.52
| 138 | 7.06
| 139 | 7.12
| 140 | 7.87
| 141 | 6.65
| 142 | 7.07
| 143 | 6.79
| 144 | 8.16
| 145 | 7.34
| 146 | 7.45
| 147 | 7.5
| 148 | 7.82
| 149 | 8.3
| 150 | 8.46
| 151 | 8.18
| 152 | 8.26
| 153 | 8.2
| 154 | 7.97
| 155 | 8.42
| 156 | 6.43
| 157 | 8.35
| 158 | 6.58
| 159 | 7.57
| 160 | 7.97
| 161 | 8.63
| 162 | 8.34
| 163 | 8.42
| 164 | 8.75
| 165 | 8.57
| 166 | 8.47
| 167 | 8.24
| 168 | 7.88
| 169 | 8.72
| 170 | 8.1
| 171 | 7.37
| 172 | 7.64
| 173 | 8.03
| 174 | 7.72
| 175 | 8.15
| 176 | 7.83
| 177 | 7.46
| 178 | 8.49
| 179 | 7.55
| 180 | 7.92
| 181 | 7.57
| 182 | 8.91
| 183 | 5.97
| 184 | 8.36
| 185 | 7.56
| 186 | 7.28
| 187 | 6.47
| 188 | 8.31
| 189 | 8.25
| 190 | 8.69
| 191 | 7.36
| 192 | 7.81
| 193 | 8.26
| 194 | 7.42
| 195 | 8.79
| 196 | 6.85
| 197 | 8.61
| 198 | 7.52
| 199 | 7.75
| 200 | 8.53
| 201 | 8.19
| 202 | 8.3
| 203 | 7.74
| 204 | 8.09
| 205 | 8.39
| 206 | 8.26
| 207 | 7.51
| 208 | 7.38
| 209 | 8.01
| 210 | 7.19
| 211 | 8.72
| 212 | 8.69
| 213 | 8.13
| 214 | 7.63
| 215 | 7.34
| 216 | 8.35
| 217 | 7.88
| 218 | 7.62
| 219 | 7.28
| 220 | 7.64
| 221 | 7.34
| 222 | 7.05
| 223 | 8.39
| 224 | 6.81
| 225 | 7.77
| 226 | 7.37
| 227 | 7.74
| 228 | 8.41
| 229 | 7.53
| 230 | 7.34
| 231 | 8.79
| 232 | 8.05
| 233 | 6.81
| 234 | 8.47
| 235 | 7.91
| 236 | 7.83
| 237 | 8.1
| 238 | 8.09
| 239 | 6.87
| 240 | 8.24
| 241 | 8.51
| 242 | 8.91
| 243 | 7.88
| 244 | 7.3
| 245 | 7.62
| 246 | 8.38
| 247 | 8.21
| 248 | 7.83
| 249 | 7.66
| 250 | 8.01
| 251 | 8.59
| 252 | 7.73
| 253 | 7.39
| 254 | 7.72
| 255 | 7.55
| 256 | 8.46
| 257 | 8.47
| 258 | 7.42
| 259 | 8.47
| 260 | 7.75
| 261 | 8.17
| 262 | 8.22
| 263 | 7.99
| 264 | 8.12
| 265 | 7.62
| 266 | 7.75
| 267 | 8.28
| 268 | 7.05
| 269 | 8.41
| 270 | 7.62
| 271 | 8.32
| 272 | 7.68
| 273 | 7.97
| 274 | 8.38
| 275 | 7.37
| 276 | 8.14
| 277 | 8.07
| 278 | 8.34
| 279 | 7.85
| 280 | 7.49
| 281 | 8.26
| 282 | 7.16
| 283 | 8.53
| 284 | 6.95
| 285 | 8.55
| 286 | 7.69
| 287 | 7.2
| 288 | 8.63
| 289 | 7.98
| 290 | 7.11
| 291 | 7.91
| 292 | 7.03
| 293 | 8.75
| 294 | 8.16
| 295 | 7.91
| 296 | 8.35
| 297 | 8.66
| 298 | 6.77
| 299 | 8.59
| 300 | 7.94
| 301 | 7.53
| 302 | 6.9
| 303 | 8.61
| 304 | 7.5
| 305 | 7.97
| 306 | 8.12
| 307 | 8.1
| 308 | 7.53
| 309 | 7.88
| 310 | 7.85
| 311 | 7.79
| 312 | 7.91
| 313 | 8.07
| 314 | 6.99
| 315 | 8.49
| 316 | 7.26
| 317 | 7.22
| 318 | 8.66
| 319 | 6.98
| 320 | 7.74
| 321 | 7.44
| 322 | 6.65
| 323 | 8.28
| 324 | 8.55
| 325 | 8
| 326 | 7.62
| 327 | 7.74
| 328 | 8.57
| 329 | 8.3
| 330 | 8.46
| 331 | 8.18
| 332 | 7.84
| 333 | 8.84
| 334 | 8.55
| 335 | 7.55
| 336 | 8.53
| 337 | 8.39
| 338 | 8.02
| 339 | 6.39
| 340 | 8.21
| 341 | 8.69
| 342 | 6.91
| 343 | 7.18
| 344 | 7.2
| 345 | 8.59
| 346 | 8.61
| 347 | 8.44
| 348 | 7.06
| 349 | 7.79
| 350 | 8.09
| 351 | 7.55
| 352 | 8.22
| 353 | 8.53
| 354 | 6.89
| 355 | 7.38
| 356 | 7.68
| 357 | 7.47
| 358 | 7.13
| 359 | 7.46
| 360 | 8.13
| 361 | 8.53
| 362 | 8.16
| 363 | 8.22
| 364 | 7.13
| 365 | 8.08
| 366 | 7.98
| 367 | 7.2
| 368 | 7.87
| 369 | 8.19
| 370 | 8.47
| 371 | 8.39
| 372 | 7.16
| 373 | 7.19
| 374 | 8.44
| 375 | 8.06
| 376 | 7.98
| 377 | 6.28
| 378 | 8.63
| 379 | 6.83
| 380 | 8.84
| 381 | 8.79
| 382 | 7.07
| 383 | 8.28
| 384 | 7.36
| 385 | 7.63
| 386 | 8.12
| 387 | 8.09
| 388 | 7.83
| 389 | 7.22
| 390 | 7.3
| 391 | 7.04
| 392 | 7.32
| 393 | 8.04
| 394 | 6.95
| 395 | 6.84
| 396 | 8.11
| 397 | 7.88
| 398 | 8.08
| 399 | 7.34
| 400 | 7.92
| 401 | 7.53
| 402 | 6.8
| 403 | 7.06
| 404 | 8.07
| 405 | 8.3
| 406 | 7.06
| 407 | 8.79
| 408 | 8.55
| 409 | 7.69
| 410 | 6.91
| 411 | 8.36
| 412 | 8.16
| 413 | 7.44
| 414 | 8.47
| 415 | 8.59
| 416 | 6.63
| 417 | 7.6
| 418 | 7.97
| 419 | 7.68
| 420 | 8.18
| 421 | 6.61
| 422 | 7.52
| 423 | 8.91
| 424 | 7.93
| 425 | 8.51
| 426 | 6.92
| 427 | 7.38
| 428 | 7.94
| 429 | 6.58
| 430 | 8.44
| 431 | 7.24
| 432 | 7.97
| 433 | 8.14
| 434 | 8.84
| 435 | 8.39
| 436 | 6.86
| 437 | 7.92
| 438 | 7.89
| 439 | 7.97
| 440 | 8.46
| 441 | 7.71
| 442 | 6.93
| 443 | 8.55
| 444 | 8.75
| 445 | 7.29
| 446 | 8.69
| 447 | 6.99
| 448 | 7.97
| 449 | 8.46
| 450 | 8.32
| 451 | 6.97
| 452 | 8.28
| 453 | 7.8
| 454 | 7.01
| 455 | 7.8
| 456 | 8.72
| 457 | 8.13
| 458 | 8.03
| 459 | 8.21
| 460 | 7.39
| 461 | 7.33
| 462 | 7.83
| 463 | 7.93
| 464 | 7.77
| 465 | 8.75
| 466 | 7.75
| 467 | 8.57
| 468 | 8.69
| 469 | 8.51
| 470 | 8.01
| 471 | 8.24
| 472 | 8.69
| 473 | 8.12
| 474 | 7.4
| 475 | 7.38
| 476 | 7.99
| 477 | 8.07
| 478 | 7.33
| 479 | 8.02
| 480 | 7.43
| 481 | 8.72
| 482 | 7.83
| 483 | 7.63
| 484 | 8.25
| 485 | 7.92
| 486 | 6.24
| 487 | 8.42
| 488 | 7.56
| 489 | 8.42
| 490 | 8.32
| 491 | 8.41
| 492 | 7.31
| 493 | 6.99
| 494 | 7.77
| 495 | 8.91
| 496 | 7.47
| 497 | 6.68
| 498 | 8.63
| 499 | 8.25
| 500 | 7.44
| 501 | 7.62
| 502 | 8.44
| 503 | 7.6
| 504 | 7.8
| 505 | 6.66
| 506 | 8.53
| 507 | 8.25
| 508 | 7.28
| 509 | 7.95
| 510 | 8.35
| 511 | 7.76
| 512 | 8.34
| 513 | 8.19
| 514 | 7.81
| 515 | 7.58
| 516 | 7.85
| 517 | 7.39
| 518 | 7.01
| 519 | 7.4
| 520 | 7.94
| 521 | 8.11
| 522 | 8.91
| 523 | 7.91
| 524 | 8.35
| 525 | 8.49
| 526 | 8.22
| 527 | 7.72
| 528 | 8.34
| 529 | 7.46
| 530 | 7.98
| 531 | 7.86
| 532 | 7
| 533 | 8.3
| 534 | 8.72
| 535 | 6.89
| 536 | 7.55
| 537 | 7.83
| 538 | 8.07
| 539 | 8.04
| 540 | 8.27
| 541 | 8.69
| 542 | 8.79
| 543 | 8.05
| 544 | 7.98
| 545 | 8.28
| 546 | 8.05
| 547 | 8.31
| 548 | 7.92
| 549 | 8.32
| 550 | 7.77
| 551 | 7.73
| 552 | 7.97
| 553 | 8.84
| 554 | 7.75
| 555 | 8.14
| 556 | 7.84
| 557 | 7.07
| 558 | 7.69
| 559 | 8.04
| 560 | 7.65
| 561 | 7.85
| 562 | 7.19
| 563 | 7.85
| 564 | 7.79
| 565 | 8.26
| 566 | 7.6
| 567 | 7.3
| 568 | 8
| 569 | 7.25
| 570 | 6.93
| 571 | 6.68
| 572 | 6.21
| 573 | 8.04
| 574 | 7.64
| 575 | 7.12
| 576 | 7.86
| 577 | 6.86
| 578 | 8.31
| 579 | 7.99
| 580 | 7.67
| 581 | 8
| 582 | 8.36
| 583 | 7.67
| 584 | 6.78
| 585 | 7.8
| 586 | 8.04
| 587 | 8.07
| 588 | 8.18
| 589 | 7.61
| 590 | 8.91
| 591 | 7.88
| 592 | 7.32
| 593 | 8.08
| 594 | 6.47
| 595 | 7.86
| 596 | 7.5
| 597 | 7.62
| 598 | 7.7
| 599 | 7.96
| 600 | 7.73
| 601 | 7.71
| 602 | 8.63
| 603 | 8.27
| 604 | 8.46
| 605 | 8.34
| 606 | 7.61
| 607 | 7.6
| 608 | 8.63
| 609 | 8.69
| 610 | 7.42
| 611 | 7.34
| 612 | 8.51
| 613 | 6.83
| 614 | 8.66
| 615 | 8.11
| 616 | 8.22
| 617 | 7.6
| 618 | 7.63
| 619 | 7.05
| 620 | 8.1
| 621 | 8.66
| 622 | 7.68
| 623 | 8.91
| 624 | 7.14
| 625 | 7.17
| 626 | 8.31
| 627 | 7.49
| 628 | 8.59
| 629 | 8.79
| 630 | 7.48
| 631 | 8.79
| 632 | 6.52
| 633 | 6.86
| 634 | 8.18
| 635 | 8.49
| 636 | 8.05
| 637 | 7.5
| 638 | 7.6
| 639 | 6.63
| 640 | 7.51
| 641 | 7.58
| 642 | 7.47
| 643 | 6.21
| 644 | 7.99
| 645 | 7.82
| 646 | 8.59
| 647 | 7.58
| 648 | 7.48
| 649 | 6.96
| 650 | 7.71
| 651 | 7.1
| 652 | 7.87
| 653 | 8.17
| 654 | 8.34
| 655 | 8.75
| 656 | 7.99
| 657 | 7.39
| 658 | 8.59
| 659 | 7.81
| 660 | 7.37
| 661 | 7.91
| 662 | 7.96
| 663 | 7.49
| 664 | 7.8
| 665 | 8.84
| 666 | 7.37
| 667 | 7.22
| 668 | 7.89
| 669 | 8.14
| 670 | 7.65
| 671 | 8.15
| 672 | 7.39
| 673 | 8.15
| 674 | 7.6
| 675 | 7.68
| 676 | 7.84
| 677 | 7.79
| 678 | 8.66
| 679 | 8.72
| 680 | 8.72
| 681 | 8.84
| 682 | 8.24
| 683 | 7.97
| 684 | 7.97
| 685 | 8.31
| 686 | 7.04
| 687 | 8.39
| 688 | 8.38
| 689 | 7.88
| 690 | 7.43
| 691 | 7.22
| 692 | 8.91
| 693 | 7.49
| 694 | 7.76
| 695 | 8.05
| 696 | 8.31
| 697 | 7.37
| 698 | 7.77
| 699 | 7.9
| 700 | 6.86
| 701 | 7.85
| 702 | 7.91
| 703 | 7.96
| 704 | 8.44
| 705 | 7.28
| 706 | 7.72
| 707 | 6.93
| 708 | 7.8
| 709 | 7.95
| 710 | 7.91
| 711 | 8.18
| 712 | 8.72
| 713 | 7.64
| 714 | 7.5
| 715 | 8.57
| 716 | 8.69
| 717 | 6.75
| 718 | 8.27
| 719 | 8.44
| 720 | 8.2
| 721 | 7.56
| 722 | 8.04
| 723 | 8.61
| 724 | 8.38
| 725 | 8.19
| 726 | 8.36
| 727 | 8.38
| 728 | 8.06
| 729 | 8.13
| 730 | 6.61
| 731 | 8.46
| 732 | 7.32
| 733 | 8.12
| 734 | 8.24
| 735 | 7.43
| 736 | 6.83
| 737 | 7.76
| 738 | 7.54
| 739 | 8.16
| 740 | 7.75
| 741 | 8.2
| 742 | 8.79
| 743 | 7.87
| 744 | 8.72
| 745 | 7.39
| 746 | 7.54
| 747 | 7.08
| 748 | 7.71
| 749 | 7.97
| 750 | 7.6
| 751 | 7.1
| 752 | 7.38
| 753 | 7.65
| 754 | 6.6
| 755 | 7.91
| 756 | 7.98
| 757 | 6.99
| 758 | 7.19
| 759 | 8.51
| 760 | 8
| 761 | 7.89
| 762 | 6.89
| 763 | 8.06
| 764 | 7.77
| 765 | 7.43
| 766 | 8.55
| 767 | 7.23
| 768 | 7.68
| 769 | 8.44
| 770 | 8.42
| 771 | 8.35
| 772 | 8.75
| 773 | 7.7
| 774 | 7.53
| 775 | 7.91
| 776 | 7.64
| 777 | 8.17
| 778 | 8.02
| 779 | 7.24
| 780 | 8.38
| 781 | 7.81
| 782 | 6.86
| 783 | 7.98
| 784 | 7.44
| 785 | 7.46
| 786 | 6.89
| 787 | 8.08
| 788 | 7.52
| 789 | 7.29
| 790 | 7.81
| 791 | 8.47
| 792 | 7.68
| 793 | 8.27
| 794 | 8.38
| 795 | 8.32
| 796 | 8.09
| 797 | 7.63
| 798 | 7.52
| 799 | 8.11
| 800 | 8.51
| 801 | 8.34
| 802 | 8.32
| 803 | 7.22
| 804 | 7.45
| 805 | 7.84
| 806 | 7.64
| 807 | 8.05
| 808 | 7.92
| 809 | 7.05
| 810 | 8.66
| 811 | 7.68
| 812 | 7.21
| 813 | 8.02
| 814 | 8.02
| 815 | 8.61
| 816 | 7.2
| 817 | 7.91
| 818 | 8.84
| 819 | 7.64
| 820 | 7.51
| 821 | 7.51
| 822 | 6.07
| 823 | 8.31
| 824 | 6.99
| 825 | 8.91
| 826 | 6.28
| 827 | 6.83
| 828 | 7.22
| 829 | 7.94
| 830 | 7.24
| 831 | 8.12
| 832 | 7.91
| 833 | 8.34
| 834 | 8.53
| 835 | 7.69
| 836 | 8.38
| 837 | 7.68
| 838 | 7.05
| 839 | 7.9
| 840 | 6.47
| 841 | 6.72
| 842 | 7.47
| 843 | 7.22
| 844 | 8.63
| 845 | 7.9
| 846 | 7.58
| 847 | 7.73
| 848 | 6.85
| 849 | 8.46
| 850 | 7.96
| 851 | 8.49
| 852 | 8.35
| 853 | 7.14
| 854 | 7.77
| 855 | 7.97
| 856 | 7.16
| 857 | 7.24
| 858 | 7.9
| 859 | 7.35
| 860 | 7.45
| 861 | 8.06
| 862 | 8.53
| 863 | 6.86
| 864 | 8.51
| 865 | 8.31
| 866 | 8.36
| 867 | 7.93
| 868 | 8.75
| 869 | 7.55
| 870 | 7.64
| 871 | 8.57
| 872 | 8.16
| 873 | 8.75
| 874 | 7.7
| 875 | 7.03
| 876 | 8.25
| 877 | 7.8
| 878 | 8.15
| 879 | 8.12
| 880 | 8.51
| 881 | 7.38
| 882 | 7.37
| 883 | 8.06
| 884 | 7.72
| 885 | 8.25
| 886 | 7.88
| 887 | 8.16
| 888 | 8.24
| 889 | 8.72
| 890 | 8.19
| 891 | 6.56
| 892 | 8.25
| 893 | 8.47
| 894 | 7.75
| 895 | 8.01
| 896 | 6.93
| 897 | 7.53
| 898 | 7.78
| 899 | 7.56
| 900 | 8.11
| 901 | 7.84
| 902 | 7.9
| 903 | 8.36
| 904 | 7.63
| 905 | 8.28
| 906 | 7.5
| 907 | 7.6
| 908 | 6.94
| 909 | 7.28
| 910 | 7.11
| 911 | 8.08
| 912 | 7.66
| 913 | 8.21
| 914 | 7.21
| 915 | 8.41
| 916 | 7.56
| 917 | 8.27
| 918 | 8.63
| 919 | 7.76
| 920 | 7.27
| 921 | 7.5
| 922 | 7.95
| 923 | 7.26
| 924 | 7.8
| 925 | 7.11
| 926 | 8.3
| 927 | 8.66
| 928 | 8
| 929 | 8.18
| 930 | 8.79
| 931 | 6.14
| 932 | 8.36
| 933 | 7.17
| 934 | 7.78
| 935 | 8.57
| 936 | 8.84
| 937 | 7.25
| 938 | 7.16
| 939 | 8.41
| 940 | 7.03
| 941 | 7.47
| 942 | 7.18
| 943 | 8.57
| 944 | 7.37
| 945 | 6.81
| 946 | 8.57
| 947 | 7.8
| 948 | 7.79
| 949 | 7.33
| 950 | 6.94
| 951 | 8.49
| 952 | 6.6
| 953 | 7.87
| 954 | 8.32
| 955 | 8.01
| 956 | 6.53
| 957 | 8.55
| 958 | 8.59
| 959 | 7.89
| 960 | 8.01
| 961 | 7.3
| 962 | 8.61
| 963 | 6.46
| 964 | 8.53
| 965 | 8.21
| 966 | 8.21
| 967 | 7.75
| 968 | 8.32
| 969 | 8.66
| 970 | 8.61
| 971 | 8.75
| 972 | 7.52
| 973 | 8.42
| 974 | 7.73
| 975 | 7.27
| 976 | 7.71
| 977 | 8.03
| 978 | 7.49
| 979 | 7.3
| 980 | 8.02
| 981 | 8.47
| 982 | 8.16
| 983 | 8.2
| 984 | 8.42
| 985 | 6.97
| 986 | 8.59
| 987 | 8.46
| 988 | 8.44
| 989 | 7.74
| 990 | 7.63
| 991 | 8.2
| 992 | 6.48
| 993 | 8.31
| 994 | 7.26
| 995 | 8.57
| 996 | 7.23
| 997 | 8.66
| 998 | 7.97
| 999 | 7.71
| 1000 | 8.41
9
0.3
6
6.3
6.6
6.9
7.2
7.5
7.8
8.1
8.4
8.7
9
0.01
0.017
0.044
0.072
0.119
0.172
0.206
0.18
0.13
0.05
0.01
0.027
0.071
0.143
0.262
0.434
0.64
0.82
0.95
1